## Excavation
Detail of Quantity
S. No. | Item of Work | No | Length (m) | Width (m) | Height (m) | Quantity (m3)
1 | Excavation Column C1 | 12 | 2.1 | 2.1 | 1.05 | 55.566
2 | Excavation Column C2 | 5 | 2.28 | 2.28 | 1.05 | 27.2916
Total | [5 empty] | 82.8576
Working Space around the main building is assumed to be 0.6m as per IS Code 1200 (Part 1): 1992

## PCC
Detail of Quantity
S. No. | Item of Work | No | Length (m) | Width (m) | Height (m) | Quantity (m3)
1 | PCC Column C1 | 12 | 0.9 | 0.9 | 0.1 | 0.972
2 | PCC Column C2 | 5 | 1.08 | 1.08 | 0.1 | 0.5832
Total | [5 empty] | 1.5552

## RCC
Detail of Quantity
S. No. | Item of Work | No | Length (m) | Width (m) | Height (m) | Quantity (m3)
1 | Upto ground level
| C1 | 12 | 0.75 | 0.75 | 0.21 | 1.4175
|  | 12 | A1=0.75x0.75 A2=0.38x0.38 H=0.19 |  |  | 0.75384
|  | 12 | 0.23 | 0.23 | 0.55 | 0.34914
| C2 | 5 | 0.9 | 0.9 | 0.225 | 0.91125
|  | 5 | A1=0.9x0.9 A2=0.45x0.45 H=0.225 |  |  | 0.53156
|  | 5 | 0.3 | 0.3 | 0.5 | 0.225
2 | Ground Level to Plinth Level
2.1 | Column
| C1 | 12 | 0.23 | 0.23 | 0.71 | 0.45071
| C2 | 5 | 0.3 | 0.3 | 0.64 | 16.68
2.2 | Slab | 1 | 17.375 | 6.095 | 0.1 | 10.5901
2.3 | Plinth Beam
| A1-B1 | 1 | 2.975 | 0.13 | 0.23 | 0.088953
| B1-C1 | 1 | 2.435 | 0.13 | 0.23 | 0.072807
| A2-B2 | 1 | 2.975 | 0.13 | 0.23 | 0.088953
| B2-C2 | 1 | 2.435 | 0.13 | 0.23 | 0.072807
| A3-B3 | 1 | 2.975 | 0.13 | 0.23 | 0.088953
| B3-C3 | 1 | 2.435 | 0.13 | 0.23 | 0.072807
| A4-B4 | 1 | 2.975 | 0.13 | 0.23 | 0.088953
| B4-C4 | 1 | 2.435 | 0.13 | 0.23 | 0.072807
| A1-A2 | 1 | 3.66 | 0.13 | 0.23 | 0.10943
| B1-B2 | 1 | 3.66 | 0.13 | 0.23 | 0.10943
| C1-C2 | 1 | 3.66 | 0.13 | 0.23 | 0.10943
| A2-A3 | 1 | 3.465 | 0.13 | 0.23 | 0.1036
| B2-B3 | 1 | 3.465 | 0.13 | 0.23 | 0.1036
| C2-C3 | 1 | 3.465 | 0.13 | 0.23 | 0.1036
| A3-A4 | 1 | 2.935 | 0.13 | 0.23 | 0.087757
| B3-B4 | 1 | 2.935 | 0.13 | 0.23 | 0.087757
| C3-C4 | 1 | 2.935 | 0.13 | 0.23 | 0.087757
| A4-A5 | 1 | 2.44 | 0.13 | 0.23 | 0.072956
| B4-B5 | 1 | 2.44 | 0.13 | 0.23 | 0.072956
| C4-C5 | 1 | 2.44 | 0.13 | 0.23 | 0.072956
| A5-C5 | 1 | 5.485 | 0.2 | 0.3 | 0.3291
| A6-B6 | 1 | 2.86 | 0.2 | 0.3 | 0.1716
| B6-C6 | 1 | 2.325 | 0.2 | 0.3 | 0.1395
| A5-A6 | 1 | 3.35 | 0.2 | 0.3 | 0.201
| B5-B6 | 1 | 3.35 | 0.2 | 0.3 | 0.201
| C5-C6 | 1 | 3.35 | 0.2 | 0.3 | 0.201
2.4 | Entrance Ramp | 1 | 6.095 | 1.575 | 0.315 | 3.0239
3 | Ground floor
3.1 | Column
| C1 | 12 | 0.23 | 0.23 | 3.21 | 2.0377
| C2 | 5 | 0.3 | 0.3 | 3.21 | 1.4445
3.2 | Slab | 1 | 18.14 | 6.095 | 0.15 | 16.5845
| Slab Decuctions (stair landing) | 1 | 2.44 | 1.22 | 0.15 | -0.44652
| Slab Decuctions (stairway) | 20 | 1.2 | 0.25 | 0.15 | -0.9
3.3 | Beam
| A1-B1 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B1-C1 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A2-B2 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B2-C2 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A3-B3 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B3-C3 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A4-B4 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B4-C4 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A1-A2 | 1 | 3.66 | 0.23 | 0.23 | 0.19361
| B1-B2 | 1 | 3.66 | 0.23 | 0.15 | 0.12627
| C1-C2 | 1 | 3.66 | 0.23 | 0.23 | 0.19361
| A2-A3 | 1 | 3.465 | 0.23 | 0.23 | 0.1833
| B2-B3 | 1 | 3.465 | 0.23 | 0.23 | 0.1833
| C2-C3 | 1 | 3.465 | 0.23 | 0.23 | 0.1833
| A3-A4 | 1 | 2.935 | 0.23 | 0.23 | 0.15526
| B3-B4 | 1 | 2.935 | 0.23 | 0.15 | 0.10126
| C3-C4 | 1 | 2.935 | 0.23 | 0.23 | 0.15526
| A4-A5 | 1 | 2.44 | 0.23 | 0.23 | 0.12908
| C4-C5 | 1 | 2.44 | 0.23 | 0.23 | 0.12908
| A5-C5 | 1 | 5.485 | 0.3 | 0.3 | 0.49365
| A6-B6 | 1 | 2.86 | 0.3 | 0.3 | 0.2574
| B6-C6 | 1 | 2.325 | 0.3 | 0.3 | 0.20925
| A5-A6 | 1 | 3.35 | 0.3 | 0.3 | 0.3015
| B5-B6 | 1 | 3.35 | 0.23 | 0.23 | 0.17722
| C5-C6 | 1 | 3.35 | 0.3 | 0.3 | 0.3015
| A6-A7 | 1 | 0.765 | 0.23 | 0.23 | 0.040469
| B6-B7 | 1 | 0.535 | 0.23 | 0.23 | 0.028302
| C6-C7 | 1 | 0.765 | 0.23 | 0.23 | 0.040469
| A7-C7 | 1 | 5.64 | 0.23 | 0.23 | 0.29836
3.4 | Stairs
| Waist Slab 1 | 1 | 3.947 | 1.2 | 0.15 | 0.71046
| Waist Slab 2 | 1 | 2.077 | 1.2 | 0.15 | 0.37386
| Stair landing | 1 | 2.44 | 1.22 | 0.15 | 0.44652
| Stairs | 20 | 1.2 | 0.25 | 0.16 | 0.48
4 | First floor
4.1 | Column
| C1 | 12 | 0.23 | 0.23 | 3.21 | 2.0377
| C2 | 5 | 0.3 | 0.3 | 3.21 | 1.4445
4.2 | Slab | 1 | 18.14 | 6.095 | 0.15 | 16.5845
| Slab Decuctions (stair landing) | 1 | 2.44 | 1.22 | 0.15 | -0.44652
| Slab Decuctions (stairway) | 20 | 1.2 | 0.25 | 0.15 | -0.9
4.3 | Beam
| A1-B1 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B1-C1 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A2-B2 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B2-C2 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A3-B3 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B3-C3 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A4-B4 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B4-C4 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A1-A2 | 1 | 3.66 | 0.23 | 0.23 | 0.19361
| B1-B2 | 1 | 3.66 | 0.23 | 0.15 | 0.12627
| C1-C2 | 1 | 3.66 | 0.23 | 0.23 | 0.19361
| A2-A3 | 1 | 3.465 | 0.23 | 0.23 | 0.1833
| B2-B3 | 1 | 3.465 | 0.23 | 0.23 | 0.1833
| C2-C3 | 1 | 3.465 | 0.23 | 0.23 | 0.1833
| A3-A4 | 1 | 2.935 | 0.23 | 0.23 | 0.15526
| B3-B4 | 1 | 2.935 | 0.23 | 0.15 | 0.10126
| C3-C4 | 1 | 2.935 | 0.23 | 0.23 | 0.15526
| A4-A5 | 1 | 2.44 | 0.23 | 0.23 | 0.12908
| C4-C5 | 1 | 2.44 | 0.23 | 0.23 | 0.12908
| A5-C5 | 1 | 5.485 | 0.3 | 0.3 | 0.49365
| A6-B6 | 1 | 2.86 | 0.3 | 0.3 | 0.2574
| B6-C6 | 1 | 2.325 | 0.3 | 0.3 | 0.20925
| A5-A6 | 1 | 3.35 | 0.3 | 0.3 | 0.3015
| B5-B6 | 1 | 3.35 | 0.23 | 0.23 | 0.17722
| C5-C6 | 1 | 3.35 | 0.3 | 0.3 | 0.3015
| A6-A7 | 1 | 0.765 | 0.23 | 0.23 | 0.040469
| B6-B7 | 1 | 0.535 | 0.23 | 0.23 | 0.028302
| C6-C7 | 1 | 0.765 | 0.23 | 0.23 | 0.040469
| A7-C7 | 1 | 5.64 | 0.23 | 0.23 | 0.29836
4.4 | Stairs
| Waist Slab 1 | 1 | 3.947 | 1.2 | 0.15 | 0.71046
| Waist Slab 2 | 1 | 2.077 | 1.2 | 0.15 | 0.37386
| Stair landing | 1 | 2.44 | 1.22 | 0.15 | 0.44652
| Stairs | 20 | 1.2 | 0.25 | 0.16 | 0.48
5 | Second floor
5.1 | Column
| C1 | 6 | 0.23 | 0.23 | 3.21 | 1.0189
5.2 | Slab | 1 | 6.1 | 4.715 | 0.15
|  | 1 | 5.2 | 3.4 | 0.15
5.3 | Beam
| A1-B1 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B1-C1 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A2-B2 | 1 | 2.975 | 0.23 | 0.23 | 0.15738
| B2-C2 | 1 | 2.435 | 0.23 | 0.23 | 0.12881
| A1-A2 | 1 | 3.66 | 0.23 | 0.23 | 0.19361
| B1-B2 | 1 | 3.66 | 0.23 | 0.15 | 0.12627
| C1-C2 | 1 | 3.66 | 0.23 | 0.23 | 0.19361
Total | [5 empty] | 91.5636
Note on E90: Tread: 250x13=3250 Riser: 160x14=2240 Hypotenuse is the length
Note on E136: Tread: 250x13=3250 Riser: 160x14=2240 Hypotenuse is the length

## Backfilling
Detail of Quantity
S. No. | Item of Work | No | Length | Width | Height | Quantity
1 | Plinth Filling | 1 | 6.095 | 17.375 | 0.54 | 57.1863
| Plinth Filling Decuctions (C1) | 12 | 0.23 | 0.23 | 0.54 | -0.34279
| Plinth Filling Decuctions (C2) | 5 | 0.3 | 0.3 | 0.54 | -0.243
2 | Gravel Filling | 1 | 6.095 | 17.375 | 0.2 | 21.1801
| Plinth Filling Decuctions (C1) | 12 | 0.23 | 0.23 | 0.2 | -0.12696
| Plinth Filling Decuctions (C2) | 5 | 0.3 | 0.3 | 0.2 | -0.09
Plinth Filling Decuctions due to beams
| A1-B1 | 1 | 2.975 | 0.13 | 0.23 | -0.088953
| B1-C1 | 1 | 2.435 | 0.13 | 0.23 | -0.072807
| A2-B2 | 1 | 2.975 | 0.13 | 0.23 | -0.088953
| B2-C2 | 1 | 2.435 | 0.13 | 0.23 | -0.072807
| A3-B3 | 1 | 2.975 | 0.13 | 0.23 | -0.088953
| B3-C3 | 1 | 2.435 | 0.13 | 0.23 | -0.072807
| A4-B4 | 1 | 2.975 | 0.13 | 0.23 | -0.088953
| B4-C4 | 1 | 2.435 | 0.13 | 0.23 | -0.072807
| A1-A2 | 1 | 3.66 | 0.13 | 0.23 | -0.10943
| B1-B2 | 1 | 3.66 | 0.13 | 0.23 | -0.10943
| C1-C2 | 1 | 3.66 | 0.13 | 0.23 | -0.10943
| A2-A3 | 1 | 3.465 | 0.13 | 0.23 | -0.1036
| B2-B3 | 1 | 3.465 | 0.13 | 0.23 | -0.1036
| C2-C3 | 1 | 3.465 | 0.13 | 0.23 | -0.1036
| A3-A4 | 1 | 2.935 | 0.13 | 0.23 | -0.087757
| B3-B4 | 1 | 2.935 | 0.13 | 0.23 | -0.087757
| C3-C4 | 1 | 2.935 | 0.13 | 0.23 | -0.087757
| A4-A5 | 1 | 2.44 | 0.13 | 0.23 | -0.072956
| B4-B5 | 1 | 2.44 | 0.13 | 0.23 | -0.072956
| C4-C5 | 1 | 2.44 | 0.13 | 0.23 | -0.072956
| A5-C5 | 1 | 5.485 | 0.2 | 0.3 | -0.3291
| A6-B6 | 1 | 2.86 | 0.2 | 0.3 | -0.1716
| B6-C6 | 1 | 2.325 | 0.2 | 0.3 | -0.1395
| A5-A6 | 1 | 3.35 | 0.2 | 0.3 | -0.201
| B5-B6 | 1 | 3.35 | 0.2 | 0.3 | -0.201
| C5-C6 | 1 | 3.35 | 0.2 | 0.3 | -0.201
3 | Foundation Filling
| Total filling of foundation for column C1 | 12 | 0.9 | 0.9 | 1.05 | 10.206
| Deduction due to volume covered by foundation C1 | 1 | From data of volume from RCC |  |  | -0.31452
| Total filling of foundation for column C2 | 5 | 1.08 | 1.08 | 1.05 | 1.2247
| Deduction due to volume covered by foundation C2 | 1 | From data of volume from RCC |  |  | -0.15469
4 | Extra Filling above ground level | 1 |  |  |  | 76.94
Total | [5 empty] | 162.4537

## Formwork
Detail of Quantity
S. No. | Item of Work | No | Length (m) | Width (m) | Quantity (m2)
1 | Upto ground level
1.1 | PCC base C1 | 48 | 0.9 | 0.1 | 4.32
| PCC base C2 | 20 | 1.08 | 0.1 | 2.16
1.2 | C1 | 48 | 0.75 | 0.21 | 7.56
|  | 48 | Height=0.268 Base1=0.38 Base=0.75 |  | 7.2682
|  | 48 | 0.23 | 0.55 | 6.072
| C2 | 20 | 0.9 | 0.25 | 4.5
|  | 20 | Height=0.318 Base1=0.45 Base=0.9 |  | 4.293
|  | 20 | 0.3 | 0.5 | 3
2 | Ground Level to Plinth Level
2.1 | Column
| C1 | 48 | 0.23 | 0.71 | 7.8384
| C2 | 20 | 0.3 | 0.64 | 3.84
2.2 | Plinth Beam
| A1-B1 | 3 | 2.975 | 0.23 | 2.0528
| B1-C1 | 3 | 2.435 | 0.23 | 1.6802
| A2-B2 | 3 | 2.975 | 0.23 | 2.0528
| B2-C2 | 3 | 2.435 | 0.23 | 1.6802
| A3-B3 | 3 | 2.975 | 0.23 | 2.0528
| B3-C3 | 3 | 2.435 | 0.23 | 1.6802
| A4-B4 | 3 | 2.975 | 0.23 | 2.0528
| B4-C4 | 3 | 2.435 | 0.23 | 1.6802
| A1-A2 | 3 | 3.66 | 0.23 | 2.5254
| B1-B2 | 3 | 3.66 | 0.23 | 2.5254
| C1-C2 | 3 | 3.66 | 0.23 | 2.5254
| A2-A3 | 3 | 3.465 | 0.23 | 2.3909
| B2-B3 | 3 | 3.465 | 0.23 | 2.3909
| C2-C3 | 3 | 3.465 | 0.23 | 2.3909
| A3-A4 | 3 | 2.935 | 0.23 | 2.0252
| B3-B4 | 3 | 2.935 | 0.23 | 2.0252
| C3-C4 | 3 | 2.935 | 0.23 | 2.0252
| A4-A5 | 3 | 2.44 | 0.23 | 1.6836
| B4-B5 | 3 | 2.44 | 0.23 | 1.6836
| C4-C5 | 3 | 2.44 | 0.23 | 1.6836
| A5-C5 | 3 | 5.485 | 0.3 | 4.9365
| A6-B6 | 3 | 2.86 | 0.3 | 2.574
| B6-C6 | 3 | 2.325 | 0.3 | 2.0925
| A5-A6 | 3 | 3.35 | 0.3 | 3.015
| B5-B6 | 3 | 3.35 | 0.3 | 3.015
| C5-C6 | 3 | 3.35 | 0.3 | 3.015
3 | Ground floor
3.1 | Column
| C1 | 48 | 0.23 | 3.21 | 35.4384
| C2 | 20 | 0.3 | 3.21 | 19.26
3.2 | Slab | 1 | 17.375 | 6.095 | 105.9006
| Slab Decuctions (stair landing) | 1 | 2.44 | 1.22 | -2.9768
| Slab Decuctions (stairway) | 20 | 1.2 | 0.25 | -6
3.3 | Beam
| A1-B1 | 1 | 2.975 | 0.23 | 0.68425
| B1-C1 | 1 | 2.435 | 0.23 | 0.56005
| A2-B2 | 1 | 2.975 | 0.23 | 0.68425
| B2-C2 | 1 | 2.435 | 0.23 | 0.56005
| A3-B3 | 1 | 2.975 | 0.23 | 0.68425
| B3-C3 | 1 | 2.435 | 0.23 | 0.56005
| A4-B4 | 1 | 2.975 | 0.23 | 0.68425
| B4-C4 | 1 | 2.435 | 0.23 | 0.56005
| A1-A2 | 1 | 3.66 | 0.23 | 0.8418
| B1-B2 | 1 | 3.66 | 0.15 | 0.549
| C1-C2 | 1 | 3.66 | 0.23 | 0.8418
| A2-A3 | 1 | 3.465 | 0.23 | 0.79695
| B2-B3 | 1 | 3.465 | 0.23 | 0.79695
| C2-C3 | 1 | 3.465 | 0.23 | 0.79695
| A3-A4 | 1 | 2.935 | 0.23 | 0.67505
| B3-B4 | 1 | 2.935 | 0.15 | 0.44025
| C3-C4 | 1 | 2.935 | 0.23 | 0.67505
| A4-A5 | 1 | 2.44 | 0.23 | 0.5612
| C4-C5 | 1 | 2.44 | 0.23 | 0.5612
| A5-C5 | 1 | 5.485 | 0.3 | 1.6455
| A6-B6 | 1 | 2.86 | 0.3 | 0.858
| B6-C6 | 1 | 2.325 | 0.3 | 0.6975
| A5-A6 | 1 | 3.35 | 0.3 | 1.005
| B5-B6 | 1 | 3.35 | 0.23 | 0.7705
| C5-C6 | 1 | 3.35 | 0.3 | 1.005
| A6-A7 | 1 | 0.765 | 0.23 | 0.17595
| B6-B7 | 1 | 0.535 | 0.23 | 0.12305
| C6-C7 | 1 | 0.765 | 0.23 | 0.17595
| A7-C7 | 1 | 5.64 | 0.23 | 1.2972
3.4 | Stairs
| Waist Slab 1 | 1 | 3.947 | 1.2 | 4.7364
| Waist Slab 1 side formwork | 1 | 3.95 | 0.31 | 1.2245
| Waist Slab 2 | 1 | 2.077 | 1.2 | 2.4924
| Waist Slab 2 side formwork | 1 | 2.077 | 0.31 | 0.64387
| Stair landing | 1 | 2.44 | 1.22 | 2.9768
| Stair riser formwork | 21 | 1.2 | 0.16 | 4.032
4 | First floor
4.1 | Column
| C1 | 48 | 0.23 | 3.21 | 35.4384
| C2 | 20 | 0.3 | 3.21 | 19.26
4.2 | Slab | 1 | 17.375 | 6.095 | 105.9006
| Slab Decuctions (stair landing) | 1 | 2.44 | 1.22 | -2.9768
| Slab Decuctions (stairway) | 20 | 1.2 | 0.25 | -6
4.3 | Beam
| A1-B1 | 1 | 2.975 | 0.23 | 0.68425
| B1-C1 | 1 | 2.435 | 0.23 | 0.56005
| A2-B2 | 1 | 2.975 | 0.23 | 0.68425
| B2-C2 | 1 | 2.435 | 0.23 | 0.56005
| A3-B3 | 1 | 2.975 | 0.23 | 0.68425
| B3-C3 | 1 | 2.435 | 0.23 | 0.56005
| A4-B4 | 1 | 2.975 | 0.23 | 0.68425
| B4-C4 | 1 | 2.435 | 0.23 | 0.56005
| A1-A2 | 1 | 3.66 | 0.23 | 0.8418
| B1-B2 | 1 | 3.66 | 0.15 | 0.549
| C1-C2 | 1 | 3.66 | 0.23 | 0.8418
| A2-A3 | 1 | 3.465 | 0.23 | 0.79695
| B2-B3 | 1 | 3.465 | 0.23 | 0.79695
| C2-C3 | 1 | 3.465 | 0.23 | 0.79695
| A3-A4 | 1 | 2.935 | 0.23 | 0.67505
| B3-B4 | 1 | 2.935 | 0.15 | 0.44025
| C3-C4 | 1 | 2.935 | 0.23 | 0.67505
| A4-A5 | 1 | 2.44 | 0.23 | 0.5612
| C4-C5 | 1 | 2.44 | 0.23 | 0.5612
| A5-C5 | 1 | 5.485 | 0.3 | 1.6455
| A6-B6 | 1 | 2.86 | 0.3 | 0.858
| B6-C6 | 1 | 2.325 | 0.3 | 0.6975
| A5-A6 | 1 | 3.35 | 0.3 | 1.005
| B5-B6 | 1 | 3.35 | 0.23 | 0.7705
| C5-C6 | 1 | 3.35 | 0.3 | 1.005
| A6-A7 | 1 | 0.765 | 0.23 | 0.17595
| B6-B7 | 1 | 0.535 | 0.23 | 0.12305
| C6-C7 | 1 | 0.765 | 0.23 | 0.17595
| A7-C7 | 1 | 5.64 | 0.23 | 1.2972
4.4 | Stairs
| Waist Slab 1 | 1 | 3.947 | 1.2 | 4.7364
| Waist Slab 1 side formwork | 1 | 3.95 | 0.31 | 1.2245
| Waist Slab 2 | 1 | 2.077 | 1.2 | 2.4924
| Waist Slab 2 side formwork | 1 | 2.077 | 0.31 | 0.64387
| Stair landing | 1 | 2.44 | 1.22 | 2.9768
| Stair riser formwork | 21 | 1.2 | 0.16 | 4.032
5 | Second floor
5.1 | Column
| C1 | 24 | 0.23 | 3.21 | 17.7192
5.2 | Slab | 1 | 6.095 | 4.115 | 25.0809
|  | 1 | 5.2 | 3.4 | 17.68
|  | 2 | 5.2 | 1.5 | 15.6
|  | 2 | 3.4 | 1.5 | 10.2
5.3 | Beam
| A1-B1 | 1 | 2.975 | 0.23 | 0.68425
| B1-C1 | 1 | 2.435 | 0.23 | 0.56005
| A2-B2 | 1 | 2.975 | 0.23 | 0.68425
| B2-C2 | 1 | 2.435 | 0.23 | 0.56005
| A1-A2 | 1 | 3.66 | 0.23 | 0.8418
| B1-B2 | 1 | 3.66 | 0.23 | 0.8418
| C1-C2 | 1 | 3.66 | 0.23 | 0.8418
Total |  |  |  |  | 577.5908
Note on E89: Tread: 250x13=3250 Riser: 160x14=2240 Hypotenuse is the length
Note on E137: Tread: 250x13=3250 Riser: 160x14=2240 Hypotenuse is the length