## Question
What is the normal duration of the project?
What is the minimum additional cost in which you can complete the project in 120 days?
What methodology can be adopted to solve this practical problem?

## Schedule
WBS ID | Activity | Original Duration | Crash duration | Predecessor ID | Lead/(Lag) | Link with Predecessor | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical Activity | Crash cost per day
1 | Building Project
A | Site Handover to Contractor (Start Milestone) | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Yes | 4000
1.1 | Structure Work
1.1.1 | Foundation
1.1.1.1 | Excavation | 3 | 1 | A | 0 | FS | 0 | 3 | 1 | 4 | -1 | - | 3000
1.1.1.2 | PCC | 3 | 3 | 1.1.1.1 | 0 | FS | 3 | 6 | 4 | 7 | -1 | - | 1000
1.1.1.3 | Reinforcement & Shuttering | 8 | 7 | 1.1.1.2 | 1 | SS | 4 | 12 | 3 | 11 | 1 | - | 3000
1.1.1.4 | Casting with RCC | 8 | 5 | 1.1.1.3 | 1 | SS | 5 | 13 | 4 | 12 | 1 | - | 4000
1.1.2 | Plinth Level
1.1.2.1 | Columns up to Plinth Beam Bottom | 7 | 4 | 1.1.1.4 | 0 | FS | 13 | 20 | 12 | 19 | 1 | - | 4000
1.1.2.2 | Backfilling & Compaction | 3 | 2 | 1.1.2.1 | 0 | FS | 20 | 23 | 19 | 22 | 1 | - | 2000
1.1.2.3 | Plinth Beam Reinf. & Shuttering | 5 | 5 | 1.1.2.2 | 0 | FS | 23 | 28 | 22 | 27 | 1 | - | 1000
1.1.2.4 | Casting of Plinth Beam with RCC | 1 | 1 | 1.1.2.3 | 0 | FS | 28 | 29 | 27 | 28 | 1 | - | 5000
1.1.2.5 | Ground Soling, Compaction & Flooring | 4 | 1 | 1.1.3.5 | 0 | FS | 29 | 33 | 24 | 28 | 5 | - | 2000
1.1.3 | First Slab
1.1.3.1 | Columns up to First Slab | 14 | 13 | 1.1.2.4 | 0 | FS | 29 | 43 | 28 | 42 | 1 | - | 2000
1.1.3.2 | Shuttering & Reinforcement of Beams & Slab | 13 | 13 | 1.1.3.1 | 2 | SS | 31 | 44 | 31 | 44 | 0 | Yes | 1000
1.1.3.3 | Casting of First Floor Beams & Slab | 1 | 1 | 1.1.3.2 | 0 | FS | 44 | 45 | 44 | 45 | 0 | Yes | 1000
1.1.3.4 | Curing Period | 21 | 21 | 1.1.3.3 | 0 | FS | 45 | 66 | 45 | 66 | 0 | Yes | 1000
1.1.3.5 | Deshuttering | 7 | 5 | 1.1.3.3 | 0 | FS | 66 | 73 | 66 | 73 | 0 | Yes | 2000
1.1.4 | Second Floor Tie Beams
1.1.4.1 | Columns up to Tie Beam Bottom | 14 | 12 | 1.1.3.3 | 0 | FS | 73 | 87 | 16 | 30 | 57 | - | 2000
1.1.4.2 | Shuttering & Reinforcement of Tie Beams | 10 | 9 | 1.1.4.1 | 2 | SS | 75 | 85 | 30 | 32 | 53 | - | 4000
1.1.4.3 | Casting of Tie Beams with RCC | 1 | 1 | 1.1.4.2 | 0 | FS | 85 | 86 | 33 | 34 | 52 | - | 6000
1.1.4.4 | Curing Period for Deshuttering | 21 | 18 | 1.1.4.3 | 0 | FS | 86 | 107 | 34 | 55 | 52 | - | 2000
1.1.4.5 | Deshuttering | 3 | 0 | 1.1.4.4 | 0 | FS | 107 | 110 | 55 | 58 | 52 | - | 4000
1.1.5 | Truss & Sheeting
1.1.5.1 | Strengthening Period for Tie Beams to Gain Strength | 7 | 7 | 1.1.4.4 | 0 | FS | 107 | 114 | 58 | 65 | 49 | - | 1000
1.1.5.2 | Truss Erection above Tie Beams | 3 | 2 | 1.1.5.1 | 0 | FS | 114 | 117 | 65 | 68 | 49 | - | 3000
1.1.5.3 | Sheeting Work | 5 | 3 | 1.1.5.2 | 0 | FS | 117 | 122 | 68 | 73 | 49 | - | 6000
1.2 | Finishing Work
1.2.1 | Blockwork, Plastering, False Ceiling Work & Tiling
1.2.1.1 | Blockwork and Plaster for Ground Floor | 14 | 14 | 1.1.3.5 | 0 | FS | 73 | 87 | 73 | 87 | 0 | Yes | 1000
1.2.1.2 | Blockwork and Plaster for First Floor | 18 | 16 | 1.1.4.5 | 0 | FS | 110 | 128 | 27 | 45 | 83 | - | 6000
1.2.1.3 | False Ceiling Work for First Floor | 8 | 5 | 1.2.1.2 | 0 | FS | 128 | 136 | 45 | 53 | 83 | - | 4000
1.2.1.4 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 8 | 1.2.1.1 | 0 | FS | 87 | 99 | 53 | 65 | 34 | - | 4000
1.2.1.5 | Tiles, Skirting & Granite Work for Ground Floor | 2 | 2 | 1.2.1.2 | 0 | FS | 128 | 130 | 65 | 67 | 63 | - | 6000
1.2.2 | Plumbing & Sanitary Works
1.2.2.1 | Plumbing & Sanitary for Ground Floor | 10 | 9 | 1.2.1.1 | 0 | FS | 87 | 97 | 67 | 77 | 20 | - | 5000
1.2.2.2 | Plumbing & Sanitary for First Floor | 10 | 9 | 1.2.2.1 | 0 | FS | 97 | 107 | 77 | 87 | 20 | - | 5000
1.2.3 | Electrification Works
1.2.3.1 | Electrification for Ground Floor | 10 | 8 | 1.2.1.1 | 0 | FS | 87 | 97 | 87 | 97 | 0 | Yes | 3000
1.2.3.2 | Electrification for First Floor | 10 | 8 | 1.2.3.1 | 0 | FS | 97 | 107 | 67 | 77 | 30 | - | 2000
1.2.4 | Doors & Windows Fixing
1.2.4.1 | Doors & Windows Fixing for Ground Floor | 10 | 8 | 1.2.1.1 | 0 | FS | 87 | 97 | 77 | 87 | 10 | - | 6000
1.2.4.2 | Doors & Windows Fixing for First Floor | 10 | 8 | 1.2.2.1 | 0 | FS | 97 | 107 | 87 | 97 | 10 | - | 1000
1.2.5 | Painting and Finishing
1.2.5.1 | Painting & Finishing for Ground Floor | 15 | 13 | 1.2.3.1 | 0 | FS | 97 | 112 | 97 | 112 | 0 | Yes | 6000
1.2.5.2 | Painting & Finishing for First Floor | 15 | 13 | 1.2.5.1 | 0 | FS | 112 | 127 | 112 | 127 | 0 | Yes | 4000
1.2.5.3 | Cleaning of Entire Structure | 5 | 4 | 1.2.5.2 | 0 | FS | 127 | 132 | 127 | 132 | 0 | Yes | 3000
B | Handover to Client (Finish Milestone) | 0 | 0 | 1.2.5.2 | 0 | FS | 132 | 132 | 132 | 132 | 0 | Yes | 2000
1000
1000+1000+1000+1000+1000+1000+1000+1000+

## Answer Sheet
1 | Normal duration is 139 days.
Steps to follow:
First find the minimum Acceleration cost for all the critical activities. This will tell that which activity to crash first.
Then crash that activity once, then critical paths may change. Again update the critical path and check the critical actvities and find the min accelerationcost.
We can crash the activities upto the crashed duration given.
These types of large networks can be solved using Primavera P6 or some algorithms which can my find all the critical activities, their accleration costs, which activity to crash and upto how much and can update the paths and total duration each time and then choose what to Crash.

## Member Name
Deepak | 220330
Shreyansh | 221031