## Team
TEAM - Original Schedule
S.no | Name | Roll no | Emai id
1 | M. Dheeraj | 241030052 | mdheeraj24@iitk.ac.in
2 | K. Phani Kumar | 241030605 | phanikk24@iitk.ac.in
TEAM - Revised Schedule
S.no | Name | Roll no | Emai id

## Shedule
SCHEDULE FOR CHANDLERS PROJECT AS A PROJECT MANAGER
Activity ID | Phase | Activity | Level | Duration | Predecesser | Relation | Lag | EST | EFT | EST(Planned) | EFT(Planned) |  |  |  | VLOOKUP(lookup_value, table_array, col_index_num, [range_lookup])
A1 | 1 | Mobilization at site | Upto GL | 3 |  |  |  | 2024-10-08 | 2024-10-11 | 2024-10-01 | 2024-10-06 | Handed the project site on 8th October. So EST changes to 8th. | Also duration changes to 3 given in Q. | Client's Delay. | $C$3:$J$148 Column C se J tak table maani, to column C acts as 1st column and J as 8th. That is why for FS it addes value of lag in 8th ie EFT and for SS it adds in 7th ie EST.
A2 | 1 | Surveying and layout | Upto GL | 2 | Mobilization at site | SS,FF | 1 | 2024-10-10 | 2024-10-12 | 2024-10-05 | 2024-10-07
A3 | 1 | Excavation for Plinth Beams, Foundation, Septic Tank | Upto GL | 2 | Surveying and layout | SS,FF | 3 | 2024-10-14 | 2024-10-16 | 2024-10-08 | 2024-10-10 | Actually started on 14th.
A4 | 1 | Form Work for PCC of Footings and Plinth Beams | Upto GL | 1 | Excavation for Plinth Beams, Foundation, Septic Tank | FS | 0 | 2024-10-16 | 2024-10-17 | 2024-10-10 | 2024-10-12 |  | Duration changed to its half and rounded to up.
A5 | 1 | PCC for Footings, Plinth Beams and Septic Tank | Upto GL | 1 | Form Work for PCC of Footings and Plinth Beams | FS | 0 | 2024-10-17 | 2024-10-18 | 2024-10-14 | 2024-10-16 | Lag changed from 2 to 0.
A6 | 1 | Reinforcement for Footings, Plinth Beams and Septic Tank | Upto GL | 2 | PCC for Footings, Plinth Beams and Septic Tank | SS,FF | 1 | 2024-10-24 | 2024-10-26 | 2024-10-15 | 2024-10-18 | Changed to 24th. 6 days of delays.
A7 | 1 | Shuttering for Footings, Plinth Beams and Septic Tank | Upto GL | 2 | Reinforcement for Footings, Plinth Beams and Septic Tank | SS,FF | 1 | 2024-10-25 | 2024-10-27 | 2024-10-16 | 2024-10-19
A8 | 1 | RCC for Footings, Plinth Beams and Septic Tank | Upto GL | 3 | Shuttering for Footings, Plinth Beams and Septic Tank | FS | 0 | 2024-10-27 | 2024-10-30 | 2024-10-19 | 2024-10-24 |  | RCC- Once started should be completed.
A9 | 1 | Deshuttering of Footings, Plinth Beams and Septic Tank | Upto GL | 1 | RCC for Footings, Plinth Beams and Septic Tank | FS | 0 | 2024-11-05 | 2024-11-06 | 2024-10-24 | 2024-10-25 | Changed from 30th to 5th due to 7th point. | Client's Delay
A10 | 2 | Reinforcement for Columns upto GL | Upto GL | 3 | Deshuttering of Footings, Plinth Beams and Septic Tank | FS | 0 | 2024-11-08 | 2024-11-11 | 2024-10-25 | 2024-10-28
A11 | 2 | Shuttering for Columns upto GL | Upto GL | 2 | Reinforcement for Columns upto GL | FS | 0 | 2024-11-11 | 2024-11-13 | 2024-10-28 | 2024-10-30
A12 | 2 | RCC for columns upto GL | Upto GL | 3 | Shuttering for Columns upto GL | FS | 0 | 2024-11-13 | 2024-11-16 | 2024-10-30 | 2024-11-02
A13 | 2 | Deshuttering of Columns upto GL | Upto GL | 2 | RCC for columns upto GL | FS | 0 | 2024-11-16 | 2024-11-18 | 2024-11-02 | 2024-11-04
A14 | 2 | Brick Work upto GL | Upto GL | 6 | Deshuttering of Columns upto GL | FS | 0 | 2024-11-18 | 2024-11-24 | 2024-11-04 | 2024-11-10
A15 | 2 | Plastering the Brick work upto GL | Upto GL | 6 | Brick Work upto GL | FS | 0 | 2024-11-24 | 2024-11-30 | 2024-11-10 | 2024-11-13 | Productivity Halfed
A16 | 2 | Water Proofing the Brick work upto GL | Upto GL | 2 | Plastering the Brick work upto GL | FS | 0 | 2024-11-30 | 2024-12-02 | 2024-11-13 | 2024-11-15
A17 | 2 | Back Filling and Compacting | Upto GL | 3 | Water Proofing the Brick work upto GL | FS | 0 | 2024-12-02 | 2024-12-05 | 2024-11-15 | 2024-11-18
A18 | 2 | Reinforcement for GL beams | Upto GL | 3 | Back Filling and Compacting | FS | 0 | 2024-12-05 | 2024-12-08 | 2024-11-18 | 2024-11-21
A19 | 2 | Shuttering for GL Beams | Upto GL | 2 | Reinforcement for GL beams | FS | 0 | 2024-12-08 | 2024-12-10 | 2024-11-21 | 2024-11-23
A20 | 2 | RCC for GL beams | Upto GL | 3 | Shuttering for GL Beams | FS | 0 | 2024-12-10 | 2024-12-13 | 2024-11-23 | 2024-11-26
A21 | 2 | Deshuttering for GlL beams after RCC | Upto GL | 2 | RCC for GL beams | FS | 0 | 2024-12-13 | 2024-12-15 | 2024-11-26 | 2024-11-28
A22 | 2 | PCC above GL for Plinth Slab | Upto GL | 4 | Deshuttering for GlL beams after RCC | FS | 0 | 2024-12-15 | 2024-12-19 | 2024-11-28 | 2024-12-02
A23 | 2 | Reinforcement for Plinth Slab | Upto GL | 3 | PCC above GL for Plinth Slab | FS | 0 | 2024-12-19 | 2024-12-22 | 2024-12-02 | 2024-12-05
A24 | 2 | RCC for Plinth Slab | Upto GL | 4 | Reinforcement for Plinth Slab | FS | 0 | 2024-12-22 | 2024-12-26 | 2024-12-05 | 2024-12-09 |  | This phase(2) may end on 15th December according to the contractor. | But, just by his statement we can't change the whole schedule.
A25 | 3 | Reinforcemnt for GF Columns of ht 3mt | Above GL upto FF | 3 | RCC for Plinth Slab | FS | 0 | 2024-12-26 | 2024-12-29 | 2024-12-09 | 2024-12-12
A26 | 3 | Shuttering for GF Columns of ht 3mt | Above GL upto FF | 2 | Reinforcemnt for GF Columns of ht 3mt | FS | 0 | 2024-12-29 | 2024-12-31 | 2024-12-12 | 2024-12-14
A27 | 3 | RCC for for GF Columns of ht 3mt | Above GL upto FF | 4 | Shuttering for GF Columns of ht 3mt | FS | 0 | 2024-12-31 | 2025-01-04 | 2024-12-14 | 2024-12-18
A28 | 3 | Deshuttering for GF Columns of ht 3mt | Above GL upto FF | 2 | RCC for for GF Columns of ht 3mt | FS | 0 | 2025-01-04 | 2025-01-06 | 2024-12-18 | 2024-12-20
A29 | 3 | Brick work for GF walls | Above GL upto FF | 5 | Deshuttering for GF Columns of ht 3mt | FS | 0 | 2025-01-06 | 2025-01-11 | 2024-12-20 | 2024-12-25
A30 | 3 | Shuttering for Staircase upto FF Slab | Above GL upto FF | 3 | Brick work for GF walls | FS | 0 | 2025-01-11 | 2025-01-14 | 2024-12-25 | 2024-12-28
A31 | 3 | Reinforcement for Staircase upto FF Slab | Above GL upto FF | 2 | Shuttering for Staircase upto FF Slab | FS | 0 | 2025-01-14 | 2025-01-16 | 2024-12-28 | 2024-12-30
A32 | 3 | RCC for Staircase upto FF Slab | Above GL upto FF | 2 | Reinforcement for Staircase upto FF Slab | FS | 0 | 2025-01-16 | 2025-01-18 | 2024-12-30 | 2025-01-01
A33 | 3 | Deshuttering for Staircase upto FF Slab | Above GL upto FF | 2 | RCC for Staircase upto FF Slab | FS | 0 | 2025-01-18 | 2025-01-20 | 2025-01-01 | 2025-01-03
A34 | 3 | Shuttering for FF Beams and Slab | Above GL upto FF | 4 | Deshuttering for Staircase upto FF Slab | SS,FF | 2 | 2025-01-20 | 2025-01-24 | 2025-01-03 | 2025-01-07
A35 | 3 | Reinforcement for FF Beams and Slab | Above GL upto FF | 4 | Shuttering for FF Beams and Slab | SS,FF | 4 | 2025-01-24 | 2025-01-28 | 2025-01-07 | 2025-01-11
A36 | 3 | RCC for FF Beams and Slab | Above GL upto FF | 4 | Reinforcement for FF Beams and Slab | FS | 0 | 2025-01-28 | 2025-02-01 | 2025-01-11 | 2025-01-15
A37 | 3 | Deshuttering of FF Beams and Slab | Above GL upto FF | 4 | RCC for FF Beams and Slab | FS | 0 | 2025-02-01 | 2025-02-05 | 2025-01-15 | 2025-01-19
A38 | 4 | Reinforcemnt for FF Columns of ht 3mt | Above FF upto SF | 3 | Deshuttering of FF Beams and Slab | FS | 0 | 2025-02-05 | 2025-02-08 | 2025-01-19 | 2025-01-22
A39 | 4 | Shuttering for FF Columns of ht 3mt | Above FF upto SF | 2 | Reinforcemnt for FF Columns of ht 3mt | FS | 0 | 2025-02-08 | 2025-02-10 | 2025-01-22 | 2025-01-24
A40 | 4 | RCC for for FF Columns of ht 3mt | Above FF upto SF | 4 | Shuttering for FF Columns of ht 3mt | FS | 0 | 2025-02-10 | 2025-02-14 | 2025-01-24 | 2025-01-28
A41 | 4 | Deshuttering for FF Columns of ht 3mt | Above FF upto SF | 2 | RCC for for FF Columns of ht 3mt | FS | 0 | 2025-02-14 | 2025-02-16 | 2025-01-28 | 2025-01-30
A42 | 4 | Brick work for FF walls | Above FF upto SF | 5 | Deshuttering for FF Columns of ht 3mt | FS | 0 | 2025-02-16 | 2025-02-21 | 2025-01-30 | 2025-02-04
A43 | 4 | Shuttering for Staircase upto SF Slab | Above FF upto SF | 3 | Brick work for FF walls | FS | 0 | 2025-02-21 | 2025-02-24 | 2025-02-04 | 2025-02-07
A44 | 4 | Reinforcement for Staircase upto SF Slab | Above FF upto SF | 2 | Shuttering for Staircase upto SF Slab | FS | 0 | 2025-02-24 | 2025-02-26 | 2025-02-07 | 2025-02-09
A45 | 4 | RCC for Staircase upto SF Slab | Above FF upto SF | 2 | Reinforcement for Staircase upto SF Slab | FS | 0 | 2025-02-26 | 2025-02-28 | 2025-02-09 | 2025-02-11
A46 | 4 | Deshuttering for Staircase upto SF Slab | Above FF upto SF | 2 | RCC for Staircase upto SF Slab | FS | 0 | 2025-02-28 | 2025-03-02 | 2025-02-11 | 2025-02-13
A47 | 4 | Shuttering for SF Beams and Slab | Above FF upto SF | 4 | Deshuttering for Staircase upto SF Slab | FS | 0 | 2025-03-02 | 2025-03-06 | 2025-02-13 | 2025-02-17
A48 | 4 | Reinforcement for SF Beams and Slab | Above FF upto SF | 4 | Shuttering for SF Beams and Slab | FS | 0 | 2025-03-06 | 2025-03-10 | 2025-02-17 | 2025-02-21
A49 | 4 | RCC for SF Beams and Slab | Above FF upto SF | 4 | Reinforcement for SF Beams and Slab | FS | 0 | 2025-03-10 | 2025-03-14 | 2025-02-21 | 2025-02-25
A50 | 4 | Deshuttering of SF Beams and Slab | Above FF upto SF | 4 | RCC for SF Beams and Slab | FS | 0 | 2025-03-14 | 2025-03-18 | 2025-02-25 | 2025-03-01
A51 | 5 | Reinforcemnt for SF Columns of ht 3mt | Above SF upto Terrace | 3 | Deshuttering of SF Beams and Slab | FS | 0 | 2025-03-18 | 2025-03-21 | 2025-03-01 | 2025-03-04
A52 | 5 | Shuttering for SF Columns of ht 3mt | Above SF upto Terrace | 2 | Reinforcemnt for SF Columns of ht 3mt | FS | 0 | 2025-03-21 | 2025-03-23 | 2025-03-04 | 2025-03-06
A53 | 5 | RCC for for SF Columns of ht 3mt | Above SF upto Terrace | 4 | Shuttering for SF Columns of ht 3mt | FS | 0 | 2025-03-23 | 2025-03-27 | 2025-03-06 | 2025-03-10
A54 | 5 | Deshuttering for SF Columns of ht 3mt | Above SF upto Terrace | 2 | RCC for for SF Columns of ht 3mt | FS | 0 | 2025-03-27 | 2025-03-29 | 2025-03-10 | 2025-03-12
A55 | 5 | Brick work for SF walls | Above SF upto Terrace | 5 | Deshuttering for SF Columns of ht 3mt | FS | 0 | 2025-03-29 | 2025-04-03 | 2025-03-12 | 2025-03-17
A56 | 5 | Shuttering for Staircase upto Terrace Slab | Above SF upto Terrace | 3 | Brick work for SF walls | FS | 0 | 2025-04-03 | 2025-04-06 | 2025-03-17 | 2025-03-20
A57 | 5 | Reinforcement for Staircase upto Terrace Slab | Above SF upto Terrace | 2 | Shuttering for Staircase upto Terrace Slab | FS | 0 | 2025-04-06 | 2025-04-08 | 2025-03-20 | 2025-03-22
A58 | 5 | RCC for Staircase upto Terrace Slab | Above SF upto Terrace | 2 | Reinforcement for Staircase upto Terrace Slab | FS | 0 | 2025-04-08 | 2025-04-10 | 2025-03-22 | 2025-03-24
A59 | 5 | Deshuttering for Staircase upto Terrace Slab | Above SF upto Terrace | 2 | RCC for Staircase upto Terrace Slab | FS | 0 | 2025-04-10 | 2025-04-12 | 2025-03-24 | 2025-03-26
A60 | 5 | Shuttering for Terrace Beams and Slab | Above SF upto Terrace | 4 | Deshuttering for Staircase upto Terrace Slab | SS,FF | 3 | 2025-04-13 | 2025-04-17 | 2025-03-27 | 2025-03-31
A61 | 5 | Reinforcement for Terrace Beams and Slab | Above SF upto Terrace | 4 | Shuttering for Terrace Beams and Slab | SS,FF | 5 | 2025-04-18 | 2025-04-22 | 2025-04-01 | 2025-04-05
A62 | 5 | RCC for Terrace Beams and Slab | Above SF upto Terrace | 4 | Reinforcement for Terrace Beams and Slab | FS | 0 | 2025-04-22 | 2025-04-26 | 2025-04-05 | 2025-04-09
A63 | 5 | Deshuttering of Terrace Beams and Slab | Above SF upto Terrace | 4 | RCC for Terrace Beams and Slab | FS | 0 | 2025-04-26 | 2025-04-30 | 2025-04-09 | 2025-04-13
A64 | 6 | Reinforcemnt for Terrace Columns of ht 1mt | Above Terrace | 2 | Deshuttering of Terrace Beams and Slab | FS | 0 | 2025-04-30 | 2025-05-02 | 2025-04-13 | 2025-04-15
A65 | 6 | Shuttering for Terrace Columns of ht 1mt | Above Terrace | 1 | Reinforcemnt for Terrace Columns of ht 1mt | FS | 0 | 2025-05-02 | 2025-05-03 | 2025-04-15 | 2025-04-16
A66 | 6 | RCC for for Terrace Columns of ht 1mt | Above Terrace | 2 | Shuttering for Terrace Columns of ht 1mt | FS | 0 | 2025-05-03 | 2025-05-05 | 2025-04-16 | 2025-04-18
A67 | 6 | Deshuttering for Terrace Columns of ht 1mt | Above Terrace | 1 | RCC for for Terrace Columns of ht 1mt | FS | 0 | 2025-05-05 | 2025-05-06 | 2025-04-18 | 2025-04-19
A68 | 6 | Brick work for Terrace parapet Wall | Above Terrace | 3 | Deshuttering for Terrace Columns of ht 1mt | FS | 0 | 2025-05-06 | 2025-05-09 | 2025-04-19 | 2025-04-22
A69 | 7 | Plastering for GF Walls, Columns, Beams and Slabs | All 3 Floors | 8 | Brick work for Terrace parapet Wall | FS | 0 | 2025-05-09 | 2025-05-17 | 2025-04-22 | 2025-04-26 |  | Productivity halfed
A70 | 7 | Plastering for FF Walls, Columns, Beams and Slabs | All 3 Floors | 8 | Plastering for GF Walls, Columns, Beams and Slabs | FS | 0 | 2025-05-17 | 2025-05-25 | 2025-04-26 | 2025-04-30 |  | Productivity halfed
A71 | 7 | Plastering for SF Walls, Columns, Beams and Slabs | All 3 Floors | 8 | Plastering for FF Walls, Columns, Beams and Slabs | FS | 0 | 2025-05-25 | 2025-06-02 | 2025-04-30 | 2025-05-04 |  | Productivity halfed
A72 | 7 | Plastering for Terrace Walls, Columns | All 3 Floors | 6 | Plastering for SF Walls, Columns, Beams and Slabs | FS | 0 | 2025-06-02 | 2025-06-08 | 2025-05-04 | 2025-05-07
A73 | 8 | Flooring in GF | All 3 Floors | 4 | Plastering for Terrace Walls, Columns | FS | 0 | 2025-06-08 | 2025-06-12 | 2025-05-07 | 2025-05-11
A74 | 8 | Flooring in FF | All 3 Floors | 4 | Flooring in GF | FS | 0 | 2025-06-12 | 2025-06-16 | 2025-05-11 | 2025-05-15
A75 | 8 | Flooring in FF | All 3 Floors | 4 | Flooring in FF | FS | 0 | 2025-06-16 | 2025-06-20 | 2025-05-15 | 2025-05-19
A76 | 8 | Installation of Doors,Windows and Carpentary works in all Floors | All 3 Floors | 15 | Flooring in FF | FS | 0 | 2025-06-16 | 2025-07-01 | 2025-05-15 | 2025-05-30
A77 | 9 | Putty Application, White Washing, Painting in GF | All 3 Floors | 4 | Installation of Doors,Windows and Carpentary works in all Floors | FS | 0 | 2025-07-01 | 2025-07-05 | 2025-05-30 | 2025-06-03
A78 | 9 | Putty Application, White Washing, Painting in FF | All 3 Floors | 4 | Putty Application, White Washing, Painting in GF | FS | 0 | 2025-07-05 | 2025-07-09 | 2025-06-03 | 2025-06-07
A79 | 9 | Putty Application, White Washing, Painting in SF | All 3 Floors | 4 | Putty Application, White Washing, Painting in FF | FS | 0 | 2025-07-09 | 2025-07-13 | 2025-06-07 | 2025-06-11
A80 | 9 | Putty Application, White Washing, Painting in Terrace | All 3 Floors | 3 | Putty Application, White Washing, Painting in SF | FS | 0 | 2025-07-13 | 2025-07-16 | 2025-06-11 | 2025-06-14
A81 | 9 | Water Proofing the Terrace Slab, Columns, Walls | All 3 Floors | 8 | Putty Application, White Washing, Painting in Terrace | FS | 0 | 2025-07-16 | 2025-07-24 | 2025-06-14 | 2025-06-22
A82 | 9 | Water proof Paint Coating on the entire External Walls outer face | All 3 Floors | 6 | Water Proofing the Terrace Slab, Columns, Walls | FS | 0 | 2025-07-24 | 2025-07-30 | 2025-06-22 | 2025-06-28
A83 | 10 | Sound Proofing/Insulating the Home theater room | In SF | 1 | Putty Application, White Washing, Painting in SF | FS | 0 | 2025-07-13 | 2025-07-14 | 2025-06-11 | 2025-06-12
A84 | 10 | Electrical works (Prewiring, Setup of projectors, speakers, cabels) | In SF | 3 | Sound Proofing/Insulating the Home theater room | FS | 0 | 2025-07-14 | 2025-07-17 | 2025-06-12 | 2025-06-15
A85 | 10 | Setting of the Seating | In SF | 1 | Electrical works (Prewiring, Setup of projectors, speakers, cabels) | FS | 0 | 2025-07-17 | 2025-07-18 | 2025-06-15 | 2025-06-16
A86 | 10 | Electrical Lighting | In SF | 1 | Setting of the Seating | FS | 0 | 2025-07-18 | 2025-07-19 | 2025-06-16 | 2025-06-17
A87 | 10 | Sanitary Works | All 3 Floors | 3 | Putty Application, White Washing, Painting in SF | FS | 0 | 2025-07-13 | 2025-07-16 | 2025-06-11 | 2025-06-14
[8 empty] | Project Completion | 2025-07-30
Find max of this everytime.
Formulas:
EFT = [EST]+[Duration]
EST = +IFS([Relation]="FS",VLOOKUP([Duration],C3:J148,8,FALSE)+[Lag], [Relation]="SS",VLOOKUP([Predecesser],C3:J148,7,FALSE)+[Lag], [Relation]="SS,FF",MAX(VLOOKUP([Predecesser],C3:J148,7,FALSE)+[Lag],VLOOKUP([Predecesser],C3:J148,8,FALSE)+[Lag]-[Duration]))
EST = +IFS([Relation]="FS",VLOOKUP([Predecesser],C4:J148,8,FALSE)+[Lag], [Relation]="SS",VLOOKUP([Predecesser],C4:J148,7,FALSE)+[Lag], [Relation]="SS,FF",MAX(VLOOKUP([Predecesser],C4:J148,7,FALSE)+[Lag],VLOOKUP([Predecesser],C4:J148,8,FALSE)+[Lag]-[Duration]))

## Sheet1
EST | EFT | Activity ID
2024-10-01 | 2024-10-06 | A1
2024-10-05 | 2024-10-07 | A2
2024-10-08 | 2024-10-10 | A3
2024-10-10 | 2024-10-12 | A4
2024-10-14 | 2024-10-16 | A5
2024-10-15 | 2024-10-18 | A6
2024-10-16 | 2024-10-19 | A7
2024-10-19 | 2024-10-24 | A8
2024-10-24 | 2024-10-25 | A9
2024-10-25 | 2024-10-28 | A10
2024-10-28 | 2024-10-30 | A11
2024-10-30 | 2024-11-02 | A12
2024-11-02 | 2024-11-04 | A13
2024-11-04 | 2024-11-10 | A14
2024-11-10 | 2024-11-13 | A15
2024-11-13 | 2024-11-15 | A16
2024-11-15 | 2024-11-18 | A17
2024-11-18 | 2024-11-21 | A18
2024-11-21 | 2024-11-23 | A19
2024-11-23 | 2024-11-26 | A20
2024-11-26 | 2024-11-28 | A21
2024-11-28 | 2024-12-02 | A22
2024-12-02 | 2024-12-05 | A23
2024-12-05 | 2024-12-09 | A24
2024-12-09 | 2024-12-12 | A25
2024-12-12 | 2024-12-14 | A26
2024-12-14 | 2024-12-18 | A27
2024-12-18 | 2024-12-20 | A28
2024-12-20 | 2024-12-25 | A29
2024-12-25 | 2024-12-28 | A30
2024-12-28 | 2024-12-30 | A31
2024-12-30 | 2025-01-01 | A32
2025-01-01 | 2025-01-03 | A33
2025-01-03 | 2025-01-07 | A34
2025-01-07 | 2025-01-11 | A35
2025-01-11 | 2025-01-15 | A36
2025-01-15 | 2025-01-19 | A37
2025-01-19 | 2025-01-22 | A38
2025-01-22 | 2025-01-24 | A39
2025-01-24 | 2025-01-28 | A40
2025-01-28 | 2025-01-30 | A41
2025-01-30 | 2025-02-04 | A42
2025-02-04 | 2025-02-07 | A43
2025-02-07 | 2025-02-09 | A44
2025-02-09 | 2025-02-11 | A45
2025-02-11 | 2025-02-13 | A46
2025-02-13 | 2025-02-17 | A47
2025-02-17 | 2025-02-21 | A48
2025-02-21 | 2025-02-25 | A49
2025-02-25 | 2025-03-01 | A50
2025-03-01 | 2025-03-04 | A51
2025-03-04 | 2025-03-06 | A52
2025-03-06 | 2025-03-10 | A53
2025-03-10 | 2025-03-12 | A54
2025-03-12 | 2025-03-17 | A55
2025-03-17 | 2025-03-20 | A56
2025-03-20 | 2025-03-22 | A57
2025-03-22 | 2025-03-24 | A58
2025-03-24 | 2025-03-26 | A59
2025-03-27 | 2025-03-31 | A60
2025-04-01 | 2025-04-05 | A61
2025-04-05 | 2025-04-09 | A62
2025-04-09 | 2025-04-13 | A63
2025-04-13 | 2025-04-15 | A64
2025-04-15 | 2025-04-16 | A65
2025-04-16 | 2025-04-18 | A66
2025-04-18 | 2025-04-19 | A67
2025-04-19 | 2025-04-22 | A68
2025-04-22 | 2025-04-26 | A69
2025-04-26 | 2025-04-30 | A70
2025-04-30 | 2025-05-04 | A71
2025-05-04 | 2025-05-07 | A72
2025-05-07 | 2025-05-11 | A73
2025-05-11 | 2025-05-15 | A74
2025-05-15 | 2025-05-19 | A75
2025-05-15 | 2025-05-30 | A76
2025-05-30 | 2025-06-03 | A77
2025-06-03 | 2025-06-07 | A78
2025-06-07 | 2025-06-11 | A79
2025-06-11 | 2025-06-14 | A80
2025-06-14 | 2025-06-22 | A81
2025-06-22 | 2025-06-28 | A82
2025-06-11 | 2025-06-12 | A83
2025-06-12 | 2025-06-15 | A84
2025-06-15 | 2025-06-16 | A85
2025-06-16 | 2025-06-17 | A86
2025-06-11 | 2025-06-14 | A87