## Question
Conduct Resource Allocation and Levelling for the following network. Can the work be performed with maximum 6 labourers without delaying the project? Has the critical path (or critical activities) changed after resource levelling excerise? What would you do if the maximum possible labour is 5 each day?
2025-10-01
Activity | Preceeding activity (FS) | Duration | Laborers | EST | EFT | LST | LFT | Critical Activity (Yes/No)
A | - | 5 | 2 | 0 | 5 | 2 | 7 | No
B | - | 7 | 4 | 0 | 7 | 0 | 7 | Yes
C | A | 3 | 3 | 5 | 8 | 9 | 12 | No
D | A,B | 5 | 3 | 7 | 12 | 7 | 12 | Yes
E | C,D | 2 | 2 | 12 | 14 | 12 | 14 | Yes

## Sheet1
Based on EST | [9 empty] | Days
Activity | Preceeding activity (FS) | Duration | Laborers | EST | EFT | LST | LFT | Critical Activity (Yes/No) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Create a bar chart from the table
A | - | 5 | 2 | 0 | 5 | 2 | 7 | No |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Resource allocation
B | - | 7 | 4 | 0 | 7 | 0 | 7 | Yes |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | A | 3 | 3 | 5 | 8 | 9 | 12 | No |  | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
D | A,B | 5 | 3 | 7 | 12 | 7 | 12 | Yes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0
E | C,D | 2 | 2 | 12 | 14 | 12 | 14 | Yes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 |  | Total Laborers
[9 empty] | Total | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 6 | 3 | 3 | 3 | 3 | 2 | 2 |  | 66
Based on LST
Activity | Preceeding activity (FS) | Duration | Laborers | EST | EFT | LST | LFT | Critical Activity (Yes/No) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Total
A | - | 5 | 2 | 0 | 5 | 2 | 7 | No |  | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
B | - | 7 | 4 | 0 | 7 | 0 | 7 | Yes |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
C | A | 3 | 3 | 5 | 8 | 9 | 12 | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 9
D | A,B | 5 | 3 | 7 | 12 | 7 | 12 | Yes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 15
E | C,D | 2 | 2 | 12 | 14 | 12 | 14 | Yes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | Total Laborers
[9 empty] | Total | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6 | 6 | 6 | 2 | 2 | 66 | 66
Then use anyone for levelling to reduce fluctuations. Reduce the fluctuations.
Levelling
Activity | Preceeding activity (FS) | Duration | Laborers | EST | EFT | LST | LFT | Critical Activity (Yes/No) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  |  |  | Dono ko dekhke combined banana hai.
A | - | 5 | 2 | 0 | 5 | 2 | 7 | Yes (Ig because now we can't dalay A as it is already standing at LFT!!) | Ye reason galat lag raha hai | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
B | - | 7 | 4 | 0 | 7 | 0 | 7 | Yes |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 |  |  | Max resource allocation kam ho jaata hai for example 7 to 6 ho gya for days 6 and 7
C | A | 3 | 3 | 5 | 8 | 9 | 12 | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 9
D | A,B | 5 | 3 | 7 | 12 | 7 | 12 | Yes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 15
E | C,D | 2 | 2 | 12 | 14 | 12 | 14 | Yes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
[9 empty] | Total | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 2 | 2

## Sheet2
Ans2 Yes after resource allocation/loading and resource levelling(Time constraint) we have seen that max 6 laborers were required for each day.
Ans3 Sir said that Activity A will also become critical!!
Ans4 Resource allocation(Resource constraint) that is we have to assign priorities to the activities on each day describing which activity will get the resources first. Then, we may have to shift the activities to upcoming days. In this process floats of activities may be utilised. And if the critical activity is shifted that may lead to the increase in the project's duration!!