## Team
TEAM - Original Schedule
S.no | Name | Roll no | Emai id
1 | M. Dheeraj | 241030052 | mdheeraj24@iitk.ac.in
2 | K. Phani Kumar | 241030605 | phanikk24@iitk.ac.in
TEAM - Revised Schedule
S.no | Name | Roll no | Emai id

## Shedule
SCHEDULE FOR CHANDLERS PROJECT AS A PROJECT MANAGER
Activity ID | Phase | Activity | Level | Duration | Predecesser | Relation | Lag | EST | EFT
A1 | 1 | Mobilization at site | Upto GL | 5 |  |  |  | 2024-10-01 | 2024-10-06
A2 | 1 | Surveying and layout | Upto GL | 2 | Mobilization at site | SS,FF | 1 | 2024-10-05 | 2024-10-07
A3 | 1 | Excavation for Plinth Beams, Foundation, Septic Tank | Upto GL | 2 | Surveying and layout | SS,FF | 3 | 2024-10-08 | 2024-10-10
A4 | 1 | Form Work for PCC of Footings and Plinth Beams | Upto GL | 2 | Excavation for Plinth Beams, Foundation, Septic Tank | FS | 0 | 2024-10-10 | 2024-10-12
A5 | 1 | PCC for Footings, Plinth Beams and Septic Tank | Upto GL | 2 | Form Work for PCC of Footings and Plinth Beams | FS | 2 | 2024-10-14 | 2024-10-16
A6 | 1 | Reinforcement for Footings, Plinth Beams and Septic Tank | Upto GL | 3 | PCC for Footings, Plinth Beams and Septic Tank | SS,FF | 1 | 2024-10-15 | 2024-10-18
A7 | 1 | Shuttering for Footings, Plinth Beams and Septic Tank | Upto GL | 3 | Reinforcement for Footings, Plinth Beams and Septic Tank | SS,FF | 1 | 2024-10-16 | 2024-10-19
A8 | 1 | RCC for Footings, Plinth Beams and Septic Tank | Upto GL | 5 | Shuttering for Footings, Plinth Beams and Septic Tank | FS | 0 | 2024-10-19 | 2024-10-24
A9 | 1 | Deshuttering of Footings, Plinth Beams and Septic Tank | Upto GL | 1 | RCC for Footings, Plinth Beams and Septic Tank | FS | 0 | 2024-10-24 | 2024-10-25
A10 | 2 | Reinforcement for Columns upto GL | Upto GL | 3 | Deshuttering of Footings, Plinth Beams and Septic Tank | FS | 0 | 2024-10-25 | 2024-10-28
A11 | 2 | Shuttering for Columns upto GL | Upto GL | 2 | Reinforcement for Columns upto GL | FS | 0 | 2024-10-28 | 2024-10-30
A12 | 2 | RCC for columns upto GL | Upto GL | 3 | Shuttering for Columns upto GL | FS | 0 | 2024-10-30 | 2024-11-02
A13 | 2 | Deshuttering of Columns upto GL | Upto GL | 2 | RCC for columns upto GL | FS | 0 | 2024-11-02 | 2024-11-04
A14 | 2 | Brick Work upto GL | Upto GL | 6 | Deshuttering of Columns upto GL | FS | 0 | 2024-11-04 | 2024-11-10
A15 | 2 | Plastering the Brick work upto GL | Upto GL | 3 | Brick Work upto GL | FS | 0 | 2024-11-10 | 2024-11-13
A16 | 2 | Water Proofing the Brick work upto GL | Upto GL | 2 | Plastering the Brick work upto GL | FS | 0 | 2024-11-13 | 2024-11-15
A17 | 2 | Back Filling and Compacting | Upto GL | 3 | Water Proofing the Brick work upto GL | FS | 0 | 2024-11-15 | 2024-11-18
A18 | 2 | Reinforcement for GL beams | Upto GL | 3 | Back Filling and Compacting | FS | 0 | 2024-11-18 | 2024-11-21
A19 | 2 | Shuttering for GL Beams | Upto GL | 2 | Reinforcement for GL beams | FS | 0 | 2024-11-21 | 2024-11-23
A20 | 2 | RCC for GL beams | Upto GL | 3 | Shuttering for GL Beams | FS | 0 | 2024-11-23 | 2024-11-26
A21 | 2 | Deshuttering for GlL beams after RCC | Upto GL | 2 | RCC for GL beams | FS | 0 | 2024-11-26 | 2024-11-28
A22 | 2 | PCC above GL for Plinth Slab | Upto GL | 4 | Deshuttering for GlL beams after RCC | FS | 0 | 2024-11-28 | 2024-12-02
A23 | 2 | Reinforcement for Plinth Slab | Upto GL | 3 | PCC above GL for Plinth Slab | FS | 0 | 2024-12-02 | 2024-12-05
A24 | 2 | RCC for Plinth Slab | Upto GL | 4 | Reinforcement for Plinth Slab | FS | 0 | 2024-12-05 | 2024-12-09
A25 | 3 | Reinforcemnt for GF Columns of ht 3mt | Above GL upto FF | 3 | RCC for Plinth Slab | FS | 0 | 2024-12-09 | 2024-12-12
A26 | 3 | Shuttering for GF Columns of ht 3mt | Above GL upto FF | 2 | Reinforcemnt for GF Columns of ht 3mt | FS | 0 | 2024-12-12 | 2024-12-14
A27 | 3 | RCC for for GF Columns of ht 3mt | Above GL upto FF | 4 | Shuttering for GF Columns of ht 3mt | FS | 0 | 2024-12-14 | 2024-12-18
A28 | 3 | Deshuttering for GF Columns of ht 3mt | Above GL upto FF | 2 | RCC for for GF Columns of ht 3mt | FS | 0 | 2024-12-18 | 2024-12-20
A29 | 3 | Brick work for GF walls | Above GL upto FF | 5 | Deshuttering for GF Columns of ht 3mt | FS | 0 | 2024-12-20 | 2024-12-25
A30 | 3 | Shuttering for Staircase upto FF Slab | Above GL upto FF | 3 | Brick work for GF walls | FS | 0 | 2024-12-25 | 2024-12-28
A31 | 3 | Reinforcement for Staircase upto FF Slab | Above GL upto FF | 2 | Shuttering for Staircase upto FF Slab | FS | 0 | 2024-12-28 | 2024-12-30
A32 | 3 | RCC for Staircase upto FF Slab | Above GL upto FF | 2 | Reinforcement for Staircase upto FF Slab | FS | 0 | 2024-12-30 | 2025-01-01
A33 | 3 | Deshuttering for Staircase upto FF Slab | Above GL upto FF | 2 | RCC for Staircase upto FF Slab | FS | 0 | 2025-01-01 | 2025-01-03
A34 | 3 | Shuttering for FF Beams and Slab | Above GL upto FF | 4 | Deshuttering for Staircase upto FF Slab | SS,FF | 2 | 2025-01-03 | 2025-01-07
A35 | 3 | Reinforcement for FF Beams and Slab | Above GL upto FF | 4 | Shuttering for FF Beams and Slab | SS,FF | 4 | 2025-01-07 | 2025-01-11
A36 | 3 | RCC for FF Beams and Slab | Above GL upto FF | 4 | Reinforcement for FF Beams and Slab | FS | 0 | 2025-01-11 | 2025-01-15
A37 | 3 | Deshuttering of FF Beams and Slab | Above GL upto FF | 4 | RCC for FF Beams and Slab | FS | 0 | 2025-01-15 | 2025-01-19
A38 | 4 | Reinforcemnt for FF Columns of ht 3mt | Above FF upto SF | 3 | Deshuttering of FF Beams and Slab | FS | 0 | 2025-01-19 | 2025-01-22
A39 | 4 | Shuttering for FF Columns of ht 3mt | Above FF upto SF | 2 | Reinforcemnt for FF Columns of ht 3mt | FS | 0 | 2025-01-22 | 2025-01-24
A40 | 4 | RCC for for FF Columns of ht 3mt | Above FF upto SF | 4 | Shuttering for FF Columns of ht 3mt | FS | 0 | 2025-01-24 | 2025-01-28
A41 | 4 | Deshuttering for FF Columns of ht 3mt | Above FF upto SF | 2 | RCC for for FF Columns of ht 3mt | FS | 0 | 2025-01-28 | 2025-01-30
A42 | 4 | Brick work for FF walls | Above FF upto SF | 5 | Deshuttering for FF Columns of ht 3mt | FS | 0 | 2025-01-30 | 2025-02-04
A43 | 4 | Shuttering for Staircase upto SF Slab | Above FF upto SF | 3 | Brick work for FF walls | FS | 0 | 2025-02-04 | 2025-02-07
A44 | 4 | Reinforcement for Staircase upto SF Slab | Above FF upto SF | 2 | Shuttering for Staircase upto SF Slab | FS | 0 | 2025-02-07 | 2025-02-09
A45 | 4 | RCC for Staircase upto SF Slab | Above FF upto SF | 2 | Reinforcement for Staircase upto SF Slab | FS | 0 | 2025-02-09 | 2025-02-11
A46 | 4 | Deshuttering for Staircase upto SF Slab | Above FF upto SF | 2 | RCC for Staircase upto SF Slab | FS | 0 | 2025-02-11 | 2025-02-13
A47 | 4 | Shuttering for SF Beams and Slab | Above FF upto SF | 4 | Deshuttering for Staircase upto SF Slab | FS | 0 | 2025-02-13 | 2025-02-17
A48 | 4 | Reinforcement for SF Beams and Slab | Above FF upto SF | 4 | Shuttering for SF Beams and Slab | FS | 0 | 2025-02-17 | 2025-02-21
A49 | 4 | RCC for SF Beams and Slab | Above FF upto SF | 4 | Reinforcement for SF Beams and Slab | FS | 0 | 2025-02-21 | 2025-02-25
A50 | 4 | Deshuttering of SF Beams and Slab | Above FF upto SF | 4 | RCC for SF Beams and Slab | FS | 0 | 2025-02-25 | 2025-03-01
A51 | 5 | Reinforcemnt for SF Columns of ht 3mt | Above SF upto Terrace | 3 | Deshuttering of SF Beams and Slab | FS | 0 | 2025-03-01 | 2025-03-04
A52 | 5 | Shuttering for SF Columns of ht 3mt | Above SF upto Terrace | 2 | Reinforcemnt for SF Columns of ht 3mt | FS | 0 | 2025-03-04 | 2025-03-06
A53 | 5 | RCC for for SF Columns of ht 3mt | Above SF upto Terrace | 4 | Shuttering for SF Columns of ht 3mt | FS | 0 | 2025-03-06 | 2025-03-10
A54 | 5 | Deshuttering for SF Columns of ht 3mt | Above SF upto Terrace | 2 | RCC for for SF Columns of ht 3mt | FS | 0 | 2025-03-10 | 2025-03-12
A55 | 5 | Brick work for SF walls | Above SF upto Terrace | 5 | Deshuttering for SF Columns of ht 3mt | FS | 0 | 2025-03-12 | 2025-03-17
A56 | 5 | Shuttering for Staircase upto Terrace Slab | Above SF upto Terrace | 3 | Brick work for SF walls | FS | 0 | 2025-03-17 | 2025-03-20
A57 | 5 | Reinforcement for Staircase upto Terrace Slab | Above SF upto Terrace | 2 | Shuttering for Staircase upto Terrace Slab | FS | 0 | 2025-03-20 | 2025-03-22
A58 | 5 | RCC for Staircase upto Terrace Slab | Above SF upto Terrace | 2 | Reinforcement for Staircase upto Terrace Slab | FS | 0 | 2025-03-22 | 2025-03-24
A59 | 5 | Deshuttering for Staircase upto Terrace Slab | Above SF upto Terrace | 2 | RCC for Staircase upto Terrace Slab | FS | 0 | 2025-03-24 | 2025-03-26
A60 | 5 | Shuttering for Terrace Beams and Slab | Above SF upto Terrace | 4 | Deshuttering for Staircase upto Terrace Slab | SS,FF | 3 | 2025-03-27 | 2025-03-31
A61 | 5 | Reinforcement for Terrace Beams and Slab | Above SF upto Terrace | 4 | Shuttering for Terrace Beams and Slab | SS,FF | 5 | 2025-04-01 | 2025-04-05
A62 | 5 | RCC for Terrace Beams and Slab | Above SF upto Terrace | 4 | Reinforcement for Terrace Beams and Slab | FS | 0 | 2025-04-05 | 2025-04-09
A63 | 5 | Deshuttering of Terrace Beams and Slab | Above SF upto Terrace | 4 | RCC for Terrace Beams and Slab | FS | 0 | 2025-04-09 | 2025-04-13
A64 | 6 | Reinforcemnt for Terrace Columns of ht 1mt | Above Terrace | 2 | Deshuttering of Terrace Beams and Slab | FS | 0 | 2025-04-13 | 2025-04-15
A65 | 6 | Shuttering for Terrace Columns of ht 1mt | Above Terrace | 1 | Reinforcemnt for Terrace Columns of ht 1mt | FS | 0 | 2025-04-15 | 2025-04-16
A66 | 6 | RCC for for Terrace Columns of ht 1mt | Above Terrace | 2 | Shuttering for Terrace Columns of ht 1mt | FS | 0 | 2025-04-16 | 2025-04-18
A67 | 6 | Deshuttering for Terrace Columns of ht 1mt | Above Terrace | 1 | RCC for for Terrace Columns of ht 1mt | FS | 0 | 2025-04-18 | 2025-04-19
A68 | 6 | Brick work for Terrace parapet Wall | Above Terrace | 3 | Deshuttering for Terrace Columns of ht 1mt | FS | 0 | 2025-04-19 | 2025-04-22
A69 | 7 | Plastering for GF Walls, Columns, Beams and Slabs | All 3 Floors | 4 | Brick work for Terrace parapet Wall | FS | 0 | 2025-04-22 | 2025-04-26
A70 | 7 | Plastering for FF Walls, Columns, Beams and Slabs | All 3 Floors | 4 | Plastering for GF Walls, Columns, Beams and Slabs | FS | 0 | 2025-04-26 | 2025-04-30
A71 | 7 | Plastering for SF Walls, Columns, Beams and Slabs | All 3 Floors | 4 | Plastering for FF Walls, Columns, Beams and Slabs | FS | 0 | 2025-04-30 | 2025-05-04
A72 | 7 | Plastering for Terrace Walls, Columns | All 3 Floors | 3 | Plastering for SF Walls, Columns, Beams and Slabs | FS | 0 | 2025-05-04 | 2025-05-07
A73 | 8 | Flooring in GF | All 3 Floors | 4 | Plastering for Terrace Walls, Columns | FS | 0 | 2025-05-07 | 2025-05-11
A74 | 8 | Flooring in FF | All 3 Floors | 4 | Flooring in GF | FS | 0 | 2025-05-11 | 2025-05-15
A75 | 8 | Flooring in FF | All 3 Floors | 4 | Flooring in FF | FS | 0 | 2025-05-15 | 2025-05-19
A76 | 8 | Installation of Doors,Windows and Carpentary works in all Floors | All 3 Floors | 15 | Flooring in FF | FS | 0 | 2025-05-15 | 2025-05-30
A77 | 9 | Putty Application, White Washing, Painting in GF | All 3 Floors | 4 | Installation of Doors,Windows and Carpentary works in all Floors | FS | 0 | 2025-05-30 | 2025-06-03
A78 | 9 | Putty Application, White Washing, Painting in FF | All 3 Floors | 4 | Putty Application, White Washing, Painting in GF | FS | 0 | 2025-06-03 | 2025-06-07
A79 | 9 | Putty Application, White Washing, Painting in SF | All 3 Floors | 4 | Putty Application, White Washing, Painting in FF | FS | 0 | 2025-06-07 | 2025-06-11
A80 | 9 | Putty Application, White Washing, Painting in Terrace | All 3 Floors | 3 | Putty Application, White Washing, Painting in SF | FS | 0 | 2025-06-11 | 2025-06-14
A81 | 9 | Water Proofing the Terrace Slab, Columns, Walls | All 3 Floors | 8 | Putty Application, White Washing, Painting in Terrace | FS | 0 | 2025-06-14 | 2025-06-22
A82 | 9 | Water proof Paint Coating on the entire External Walls outer face | All 3 Floors | 6 | Water Proofing the Terrace Slab, Columns, Walls | FS | 0 | 2025-06-22 | 2025-06-28
A83 | 10 | Sound Proofing/Insulating the Home theater room | In SF | 1 | Putty Application, White Washing, Painting in SF | FS | 0 | 2025-06-11 | 2025-06-12
A84 | 10 | Electrical works (Prewiring, Setup of projectors, speakers, cabels) | In SF | 3 | Sound Proofing/Insulating the Home theater room | FS | 0 | 2025-06-12 | 2025-06-15
A85 | 10 | Setting of the Seating | In SF | 1 | Electrical works (Prewiring, Setup of projectors, speakers, cabels) | FS | 0 | 2025-06-15 | 2025-06-16
A86 | 10 | Electrical Lighting | In SF | 1 | Setting of the Seating | FS | 0 | 2025-06-16 | 2025-06-17
A87 | 10 | Sanitary Works | All 3 Floors | 3 | Putty Application, White Washing, Painting in SF | FS | 0 | 2025-06-11 | 2025-06-14
Formulas:
EFT = [EST]+[Duration]
EST = +IFS([Relation]="FS",VLOOKUP([Duration],C3:J148,8,FALSE)+[Relation], [Relation]="SS",VLOOKUP([Predecesser],C3:J148,7,FALSE)+[Lag], [Relation]="SS,FF",MAX(VLOOKUP([Predecesser],C3:J148,7,FALSE)+[Lag],VLOOKUP([Predecesser],C3:J148,8,FALSE)+[Lag]-[Duration]))
EST = +IFS([Relation]="FS",VLOOKUP([Predecesser],C4:J148,8,FALSE)+[Lag], [Relation]="SS",VLOOKUP([Predecesser],C4:J148,7,FALSE)+[Lag], [Relation]="SS,FF",MAX(VLOOKUP([Predecesser],C4:J148,7,FALSE)+[Lag],VLOOKUP([Predecesser],C4:J148,8,FALSE)+[Lag]-[Duration]))