## Sheet2
Activity | Duration (days) | Relationship | ES | EF | Relation type | Lag | 2025-01-01
A – Earthwork | 4 |  | 2025-01-01 | 2025-01-29
B - Steel fabrication | 1 |  | 2025-01-01 | 2025-01-08
C - Shuttering fabrication | 5 |  | 2025-01-01 | 2025-02-05
D - Plain cement concrete (PCC) | 5 | A – Earthwork | 2025-01-31 | 2025-03-07 | FS | 2
E - Rebar transportation | 1 | B - Steel fabrication,D - Plain cement concrete (PCC) | 2025-01-31 | 2025-02-07 | FS,SF | 1,1
F - Concreting of raft | 2 | D - Plain cement concrete (PCC),D - Plain cement concrete (PCC),E - Rebar transportation | 2025-03-06 | 2025-03-20 | SS,FF,FS | 7,1,0
G - Wall shuttering | 1 | C - Shuttering fabrication,F - Concreting of raft | 2025-03-06 | 2025-03-13 | FS,SF | 1,1
H - Concreting of wall | 10 | G - Wall shuttering,F - Concreting of raft,F - Concreting of raft | 2025-03-13 | 2025-05-22 | FS,SS,FF | 0,1,3
I - Fencing | 5 | H - Concreting of wall | 2025-05-22 | 2025-06-26 | FS | 0
2025-06-26
Formulas:
EF = Schedule2[[#This Row],[ES]] + Schedule2[[#This Row],[Duration (days)]]*7
EF = MAX(G4:[EF, row above])

## Name
Ramji | 220869
Deepak | 220330
shreyansh | 221031

## Sheet4
Month | description of work done | 15571000
1 | Earthwork
Steel fabrication
85.7% of shuttering
2 | 80% PCC | 3029000
Rebar
14.4% shuttering
3 | 20% PCC | 13171000
concreting of raft
wall shuttering
25.7% of concreting of wall
4 | 42.6% of concreting of wall | 1278000
5 | 31.7% concreting of wall | 1208000
25.7% fencing
6 | 74.3% fencing | 743000
| Activity | Billing amount
| A – Earthwork | 3000000
| B - Steel fabrication | 10000000
| C - Shuttering fabrication | 3000000
| D - Plain cement concrete (PCC) | 2000000
| E - Rebar transportation | 1000000
| F - Concreting of raft | 10000000
| G - Wall shuttering | 2000000
| H - Concreting of wall | 3000000
| I - Fencing | 1000000
35000000

## Sheet3
Activity | Billing amount
A – Earthwork | 3000000
B - Steel fabrication | 10000000
C - Shuttering fabrication | 3000000
D - Plain cement concrete (PCC) | 2000000
E - Rebar transportation | 1000000
F - Concreting of raft | 10000000
G - Wall shuttering | 2000000
H - Concreting of wall | 3000000
I - Fencing | 1000000
35000000

## cash flow
Months | Inflow
1 | 4200000
3 | 14731000
4 | 2189000
5 | 12331000
6 | 438000
7 | 368000
8 | 743000