## Sheet1
Assumption Part IS Code : IS 7272 Part 1 ,IS 15883 Part 1,2
Q1 | Appropriate level of detail to use for activities?
Q2 | Appropriate cycle for gathering project status and updating schedule
Q3 | What should be the time scale to be used?
Q4 | Will resource availability be considered during scheduling?
Assumption (underline Assumptions)
1 | Project type: a typical reinforced-concrete 3-storey house G+2 (ground + 1st + 2nd) (no basement).
2 | Footprint and grids: plan spans organized on grids A–C/1–6 with overall building envelope approximately 18.135 m (longitudinal) by 6.095 m (transverse) per beam layout for scoping quantities and sequencing.
3 | Levels and verticals: Parking +300, Entrance +940, First Floor +4300, Second Floor +7660, Mumty/Terrace +10060 adopted for all level‑based takeoffs and schedule restraints
4 | Structural thicknesses: slab thickness 160 mm, plinth slab thickness 100 mm, floor‑to‑floor height 3360 mm, footing depth −1050 mm; use these for volume/formwork and vertical clearances unless superseded by detail.
5 | Stairs geometry: stair width 1200 mm, tread 250 mm, riser 160 mm for waist slab and finishing quantities and to define stair sequencing across levels
6 | Openings: door/window/vent sizes and types per schedule (D1–D4, W1–W3, V1, S1) for masonry deductions, frames, shutters, glazing, and finishing.
7 | Beam system: beam marks B1–B4 and plinth beams define structural sequencing for column→beam→slab cycles on each floor.
8 | Terrace scope: mumty rooms, parapets, terrace chhajja, and waterproofing/finish items included in superstructure scope
9 | Measurement standard: quantities measured per IS measurement code referenced in assignment, including working space for excavation and transparent computation columns in Excel
10 | Site availability: assume site handover and start readiness from 01‑Oct‑2025; adjust if client or institute issues a different mobilization date.
11 | Working calendar: 6‑day site calendar (Mon–Sat working, Sunday non‑working) unless the project issues a different calendar
12 | Time unit and updates: use days as schedule unit with a weekly update cycle for progress measurement and control
13 | Activity sizing: plan activities so no single activity exceeds 14 calendar days; target durations ≤ 2× the weekly update cycle as per lecture best practice.
14 | Logic discipline: use FS as default relationship; apply SS/FF only where physically justified; avoid negative lags and do not use constraints to replace logic.
15 | Finishes sequencing: masonry → internal plaster → flooring → doors/windows shutters → internal painting per floor; terrace waterproofing precedes terrace finishes
16 | MEP sleeves: allowance for sleeves/openings through slabs/beams to be coordinated during reinforcement stage on each floor
17 | External works: entrance ramp 1:5 and approach works sequenced after external plaster/painting and terrace drainage completion.
Q1 | Appropriate level of detail to use for activities?
Use a floor-based WBS: Substructure/Plinth, Ground Floor (+940), First (+4300), Second (+7660), and Mumty/Terrace (+10060), with activities grouped by structural and architectural trades on each level.
For structure, package each floor as columns → beams → slab → stairs with separate entries for shuttering, rebar, and concreting only where overlaps are physically meaningful, avoiding excessive micro-steps.
For finishes/MEP, keep activities at trade-by-floor (masonry, frames, rough-ins, internal plaster, flooring, door/window shutters, painting, external plaster, waterproofing/terrace works) rather than room-by-room
Target durations ≤ 14 days so no task exceeds twice the weekly update cycle, and ensure every activity has at least one predecessor and successor with FS as default and limited SS/FF only where physically justified.
Avoid using constraints to replace logic and avoid negative lags; document the basis for any restraints or overlaps to maintain schedule transparency.
Q2 | Appropriate cycle for gathering project status and updating schedule
Weekly cycle: capture daily field logs, freeze progress every Friday (cut‑off), update the CPM on Monday with actuals and remaining durations, review critical/near‑critical paths, and publish a 2‑week look‑ahead on a 6‑day working calendar using day units.
During high‑risk or milestone weeks, add a mid‑week mini‑update; keep the contractual baseline frozen and document any logic/lag changes in the basis‑of‑schedule
Q3 | What should be the time scale to be used?
Use day as the primary time scale on a 6‑day working calendar (Mon–Sat)
Day units align with activity sizing and progress measurement by quantities; avoid hour‑level noise and maintain consistency across floors and trades.
Keep calendar exceptions for Sundays/holidays and document any shift changes; do not replace logic with date constraints when re‑forecasting
Q4 | Will resource availability be considered during scheduling?
Yes
Baseline: develop CPM using physical FS/SS links; size durations via TE=q/(p×n) using IS time‑management and labour outputs.
Review: check peak demand for shuttering carpenters, steel fixers, concreting, masons, tilers, plumbers, and electricians by week; adjust crew splits or sequence to remove overloads without hard dates
Document: record the basis for any resource‑driven restraint/lag; keep the contractual baseline frozen and track variances weekly in the look‑ahead and risk logs.

## Sheet2
2025-10-01
Activity | Description | Duration (days) | Relationship | ES | EF | Relation type | Lag | Work | Crew_n | Number of people per crew | TE_calc_days | Calculations based on TE=q/(p x n) | Resources before levelling | Resources after levelling | Duration before levelling | Duration after levelling
A001 | Project mobilization and site setup (office, store, security) | 5 |  | 2025-10-01 | 2025-10-06 |  |  | Preliminaries | 1 | 4 |  | Time-boxed per plan (no TE calc) | 4 | 4 | 5 | 5
A002 | Site survey and setting-out (grids A–C/1–6) | 3 | A001 | 2025-10-06 | 2025-10-09 | FS | 0 | Survey | 1 | 3 |  | Time-boxed survey window | 3 | 3 | 3 | 3
A003 | Permits and clearances (admin) | 10 | A001 | 2025-10-01 | 2025-10-11 | SS | 0 | Admin | 1 | 2 |  | Admin duration (no quantity) | 2 | 2 | 10 | 10
A004 | Temporary fencing and HSE installations | 3 | A001 | 2025-10-06 | 2025-10-09 | FS | 0 | HSE | 1 | 4 |  | Enablement duration | 4 | 4 | 3 | 3
A005 | Temporary utilities (power/water/lighting) | 4 | A001 | 2025-10-06 | 2025-10-10 | FS | 0 | Temporary Utilities | 1 | 4 |  | Enablement duration | 4 | 4 | 4 | 4
A006 | Procurement plan and long-lead identification | 4 | A001 | 2025-10-06 | 2025-10-10 | FS | 0 | Procurement | 1 | 2 |  | Planning task | 2 | 2 | 4 | 4
A007 | Geotech verification / soil check (if required) | 3 | A001 | 2025-10-06 | 2025-10-09 | FS | 0 | Geotech | 1 | 3 |  | Allowance if triggered | 3 | 3 | 3 | 3
A008 | Method statements / ITP approvals | 3 | A001 | 2025-10-06 | 2025-10-09 | FS | 0 | QA/QC | 1 | 2 |  | Document approvals | 2 | 2 | 3 | 3
A009 | Set up yards (bar-bending, formwork & storage) | 2 | A001 | 2025-10-06 | 2025-10-08 | FS | 0 | Preliminaries | 1 | 4 |  | Enablement task | 4 | 4 | 2 | 2
A010 | Site clearing and access preparation | 3 | A004 | 2025-10-11 | 2025-10-14 | FS | 2 | Earthwork | 1 | 5 | 1.8 | TE≈105.9/(60×1)=1.77 → rounded → 3 d (access/setup) | 5 | 5 | 2 | 3
A011 | Excavation to founding level per footing grid | 7 | A010 | 2025-10-16 | 2025-10-23 | FS | 2 | Earthwork | 1 | 6 | 6.9 | TE=82.8576/(12×1)=6.90 → 7 d (from Excel Excavation) | 6 | 6 | 7 | 7
A012 | Dewatering and temporary drainage (if required) | 3 | A011 | 2025-10-18 | 2025-10-21 | SS | 2 | Dewatering | 1 | 3 |  | Contingency allowance | 3 | 3 | 3 | 3
A013 | PCC blinding under footings | 1 | A011 | 2025-10-25 | 2025-10-26 | FS | 2 | Concreting | 1 | 6 | 0.2 | TE=1.5552/(8×1)=0.19 → 1 d (from Excel PCC) | 6 | 6 | 1 | 1
A014 | Footing formwork/boxing | 3 | A013 | 2025-10-27 | 2025-10-30 | FS | 1 | Formwork | 1 | 3 | 3 | From Excel formwork footing subtotals; TE≈3 d | 3 | 3 | 3 | 3
A015 | Footing reinforcement placement | 2 | A014 | 2025-10-28 | 2025-10-30 | SS | 1 | Rebar | 1 | 4 | 2 | TE=12/(6×1)=2 d | 4 | 4 | 2 | 2
A016 | Footing concreting | 3 | A015 | 2025-10-30 | 2025-11-02 | FS | 0 | Concreting | 1 | 8 | 3 | Footing pour spread with blinding; keep 3 d for crew cycle | 8 | 8 | 3 | 3
A017 | Strip footing formwork | 1 | A016 | 2025-11-03 | 2025-11-04 | FS | 1 | Formwork | 1 | 3 |  | Strike/stack allowance | 3 | 3 | 1 | 1
A018 | Backfill around footings in layers | 1 | A017 | 2025-11-05 | 2025-11-06 | FS | 1 | Backfill | 1 | 6 | 1 | TE=10/(10×1)=1 d (local around pedestals) | 6 | 6 | 1 | 1
A019 | Column starter/pedestal shuttering | 2 | A016 | 2025-11-03 | 2025-11-05 | FS | 1 | Formwork | 1 | 3 | 2 | TE=12/6=2 d | 3 | 3 | 2 | 2
A020 | Column starter/pedestal reinforcement | 2 | A019 | 2025-11-04 | 2025-11-06 | SS | 1 | Rebar | 1 | 4 | 2 | TE=12/6=2 d | 4 | 4 | 2 | 2
A021 | Column starter/pedestal concreting | 1 | A020 | 2025-11-06 | 2025-11-07 | FS | 0 | Concreting | 1 | 6 | 0.5 | Small pour; 1 d | 6 | 6 | 1 | 1
A022 | Plinth beam shuttering (per plinth layout) | 5 | A021 | 2025-11-08 | 2025-11-13 | FS | 1 | Formwork | 1 | 3 | 4.7 | From Excel formwork plinth subtotals; TE≈4.7 → 5 d | 3 | 3 | 5 | 5
A023 | Plinth beam reinforcement | 2 | A022 | 2025-11-09 | 2025-11-11 | SS | 1 | Rebar | 1 | 4 | 1.9 | TE≈1.9 → 2 d | 4 | 4 | 2 | 2
A024 | Plinth beam concreting | 1 | A023 | 2025-11-11 | 2025-11-12 | FS | 0 | Concreting | 1 | 8 | 0.5 | TE≈0.5 → 1 d | 8 | 8 | 1 | 1
A025 | Plinth backfill and compaction | 9 | A024 | 2025-11-14 | 2025-11-23 | FS | 2 | Backfill | 1 | 6 | 8.1 | TE=162.4537/(20×1)=8.12 → 9 d (Backfilling sheet total) | 6 | 6 | 9 | 9
A026 | Anti-termite treatment at plinth | 1 | A025 | 2025-11-23 | 2025-11-24 | FS | 0 | Chemical Treatment | 1 | 3 | 0.5 | TE≈0.53 → 1 d | 3 | 3 | 1 | 1
A027 | PCC sub-base at ground floor level | 2 | A026 | 2025-11-24 | 2025-11-26 | FS | 0 | Concreting | 1 | 4 | 1.3 | Drawing-based PCC; workbook has RCC separately | 6 | 4 | 2 | 2
A028 | Ground floor columns shuttering up to beam soffit | 2 | A024 | 2025-11-13 | 2025-11-15 | FS | 1 | Formwork | 1 | 8 | 2 | TE=12/6=2 d | 3 | 8 | 2 | 2
A029 | Ground floor column reinforcement | 2 | A028 | 2025-11-14 | 2025-11-16 | SS | 1 | Rebar | 1 | 3 | 2 | TE=2 d | 4 | 3 | 2 | 2
A030 | Ground floor column concreting | 1 | A029 | 2025-11-16 | 2025-11-17 | FS | 0 | Concreting | 1 | 6 | 0.6 | TE≈0.6 → 1 d (RCC GF column vol) | 8 | 6 | 1 | 1
A031 | Ground floor beam and slab formwork | 9 | A030 | 2025-11-18 | 2025-11-27 | FS | 1 | Formwork | 1 | 6 | 8.1 | TE=96.924/(12×1)=8.08 → 9 d | 3 | 6 | 9 | 9
A032 | Ground floor beam reinforcement | 3 | A031 | 2025-11-26 | 2025-11-29 | SS | 8 | Rebar | 1 | 10 | 2.9 | TE≈2.9 → 3 d | 6 | 10 | 3 | 3
A033 | Ground floor slab reinforcement and MEP sleeves | 3 | A031 | 2025-11-29 | 2025-12-02 | SS | 11 | Rebar/MEP | 1 | 6 | 2.4 | TE≈2.4 → 3 d (rebar + MEP) | 6 | 6 | 3 | 3
A034 | Ground floor beam and slab concreting | 3 | A032,A033 | 2025-12-02 | 2025-12-05 | FS,FS | 0,0 | Concreting | 1 | 3 | 2.5 | TE=15.238/6=2.54 → 3 d (RCC slab net pour) | 10 | 3 | 3 | 3
A035 | Stair flight GF→FF casting (waist/landing) | 1 | A030,A034 | 2025-12-06 | 2025-12-07 | FS,FS | 1,1 | Concreting | 1 | 4 | 0.3 | TE≈0.34 → 1 d (RCC stairs + landing) | 6 | 4 | 1 | 1
A036 | First floor columns shuttering | 2 | A034 | 2025-12-07 | 2025-12-09 | FS | 2 | Formwork | 1 | 8 | 2 | TE=2 d | 3 | 8 | 2 | 2
A037 | First floor column reinforcement | 2 | A036 | 2025-12-08 | 2025-12-10 | SS | 1 | Rebar | 1 | 3 | 2 | TE=2 d | 4 | 3 | 2 | 2
A038 | First floor column concreting | 1 | A037 | 2025-12-10 | 2025-12-11 | FS | 0 | Concreting | 1 | 6 | 0.6 | TE≈0.6 → 1 d | 8 | 6 | 1 | 1
A039 | First floor beam and slab formwork | 9 | A038 | 2025-12-12 | 2025-12-21 | FS | 1 | Formwork | 1 | 6 | 8.1 | TE≈8.08 → 9 d | 3 | 6 | 9 | 9
A040 | First floor beam reinforcement | 3 | A039 | 2025-12-20 | 2025-12-23 | SS | 8 | Rebar | 1 | 10 | 2.9 | TE≈2.9 → 3 d | 6 | 10 | 3 | 3
A041 | First floor slab reinforcement and MEP sleeves | 3 | A039 | 2025-12-23 | 2025-12-26 | SS | 11 | Rebar/MEP | 1 | 6 | 2.4 | TE≈2.4 → 3 d | 6 | 6 | 3 | 3
A042 | First floor beam and slab concreting | 3 | A040,A041 | 2025-12-26 | 2025-12-29 | FS,FS | 0,0 | Concreting | 1 | 3 | 2.5 | TE≈2.54 → 3 d | 10 | 3 | 3 | 3
A043 | Stair flight FF→SF casting | 1 | A038,A042 | 2025-12-30 | 2025-12-31 | FS,FS | 1,1 | Concreting | 1 | 4 | 0.3 | TE≈0.34 → 1 d | 6 | 4 | 1 | 1
A044 | Second floor columns shuttering | 2 | A042 | 2025-12-31 | 2026-01-02 | FS | 2 | Formwork | 1 | 8 | 1 | TE=6/6=1 → 2 d for cycle consistency | 3 | 8 | 2 | 2
A045 | Second floor column reinforcement | 2 | A044 | 2026-01-01 | 2026-01-03 | SS | 1 | Rebar | 1 | 3 | 1 | TE≈1 → 2 d for cycle consistency | 4 | 3 | 2 | 2
A046 | Second floor column concreting | 1 | A045 | 2026-01-03 | 2026-01-04 | FS | 0 | Concreting | 1 | 6 | 0.2 | TE≈0.17 → 1 d | 8 | 6 | 1 | 1
A047 | Second floor beam and slab formwork | 6 | A046 | 2026-01-05 | 2026-01-11 | FS | 1 | Formwork | 1 | 6 | 5.7 | TE=68.561/(12×1)=5.71 → 6 d (roof/mumty slab areas) | 3 | 6 | 6 | 6
A048 | Second floor beam reinforcement | 3 | A047 | 2026-01-11 | 2026-01-14 | SS | 6 | Rebar | 1 | 10 | 3 | Allow 3 d for smaller beam set | 6 | 10 | 3 | 3
A049 | Second floor slab reinforcement and MEP sleeves | 3 | A047 | 2026-01-14 | 2026-01-17 | SS | 9 | Rebar/MEP | 1 | 6 | 1.7 | TE≈1.7 → 3 d for coordination | 6 | 6 | 3 | 3
A050 | Second floor beam and slab concreting | 2 | A048,A049 | 2026-01-17 | 2026-01-19 | FS,FS | 0,0 | Concreting | 1 | 3 | 1.7 | TE=(68.561×0.15)/6 ≈1.71 → 2 d | 10 | 3 | 2 | 2
A051 | Stair flight SF→Terrace/Mumty casting | 1 | A046,A050 | 2026-01-20 | 2026-01-21 | FS,FS | 1,1 | Concreting | 1 | 6 | 0.2 | Small pour; 1 d | 6 | 6 | 1 | 1
A052 | Mumty/terrace roof shuttering (beams/slab/chhajja) | 6 | A050 | 2026-01-21 | 2026-01-27 | FS | 2 | Formwork | 1 | 5 | 5.7 | Same as A047 if separate package | 3 | 5 | 6 | 6
A053 | Mumty/terrace roof reinforcement and sleeves | 3 | A052 | 2026-01-23 | 2026-01-26 | SS | 2 | Rebar | 1 | 5 | 1.7 | TE≈1.7 → 3 d | 6 | 5 | 3 | 3
A054 | Mumty/terrace slab concreting | 2 | A053 | 2026-01-26 | 2026-01-28 | FS | 0 | Concreting | 1 | 4 | 1.7 | TE≈1.7 → 2 d | 10 | 4 | 2 | 2
A055 | Parapet and mumty wall masonry | 2 | A054 | 2026-01-30 | 2026-02-01 | FS | 2 | Masonry | 1 | 6 | 1.5 | TE≈1.5 → 2 d | 6 | 6 | 2 | 2
A056 | Terrace waterproofing base preparation | 1 | A054 | 2026-02-04 | 2026-02-05 | FS | 7 | Waterproofing | 1 | 6 | 0.3 | TE≈0.34 → 1 d; 7 d curing lag before WP | 5 | 6 | 1 | 1
A057 | Terrace waterproofing application | 1 | A056 | 2026-02-06 | 2026-02-07 | FS | 1 | Waterproofing | 1 | 6 | 0.5 | TE≈0.46 → 1 d | 5 | 6 | 2 | 1
A058 | Terrace finishes/tiles and rainwater fittings | 3 | A057 | 2026-02-08 | 2026-02-11 | FS | 1 | Tiling | 1 | 4 | 2.9 | TE≈2.86 → 3 d | 4 | 4 | 2 | 3
A059 | Ground floor masonry (external/internal, ducts) | 14 | A034 | 2025-12-07 | 2025-12-21 | FS | 2 | Masonry | 1 | 4 | 13.5 | Drawing-based take-off retained (no masonry sheet) | 6 | 4 | 14 | 14
A060 | First floor masonry (external/internal) | 14 | A042,A059 | 2025-12-29 | 2026-01-12 | FS,FS | 0,2 | Masonry | 1 | 5 | 13.5 | As above | 6 | 5 | 14 | 14
A061 | Second floor masonry (external/internal) | 14 | A050,A060 | 2026-01-19 | 2026-02-02 | FS,FS | 0,2 | Masonry | 1 | 4 | 13.5 | As above | 6 | 4 | 14 | 14
A062 | Mumty/store wall masonry | 2 | A054 | 2026-01-30 | 2026-02-01 | FS | 2 | Masonry | 1 | 4 | 2 | TE=2 d | 4 | 4 | 2 | 2
A063 | Door and window frames install GF+FF | 5 | A059,A060 | 2026-01-13 | 2026-01-18 | FS,FS | 1,1 | Joinery | 1 | 4 | 5 | TE=5 d | 4 | 4 | 5 | 5
A064 | Door and window frames install SF+Mumty | 3 | A061,A062 | 2026-02-03 | 2026-02-06 | FS,FS | 1,1 | Joinery | 1 | 4 | 3 | TE=3 d | 4 | 4 | 3 | 3
A065 | Plumbing stacks and underground drainage tie-ins | 5 | A027 | 2025-11-26 | 2025-12-01 | FS | 0 | Plumbing | 1 | 4 |  | Time-boxed UG works/testing | 5 | 4 | 5 | 5
A066 | Electrical conduits rough-in GF+FF | 6 | A059,A063 | 2026-01-19 | 2026-01-25 | FS,FS | 2,1 | Electrical | 1 | 4 | 6 | TE≈6 d (2 floors @0.33 floor/day → ~6 d) | 4 | 4 | 6 | 6
A067 | Electrical conduits rough-in SF+Mumty | 5 | A061,A064 | 2026-02-07 | 2026-02-12 | FS,FS | 2,1 | Electrical | 1 | 6 | 4.5 | TE≈4.5 → 5 d | 4 | 6 | 5 | 5
A068 | Internal plaster GF+FF | 33 | A063,A066 | 2026-01-27 | 2026-03-01 | FS,FS | 2,2 | Plaster | 1 | 6 | 32.8 | TE≈32.8 → 33 d | 4 | 6 | 33 | 33
A069 | Internal plaster SF+Mumty | 17 | A064,A067,A068 | 2026-03-06 | 2026-03-23 | FS,FS,FS | 2,2,5 | Plaster | 1 | 4 | 16.4 | TE≈16.4 → 17 d | 4 | 4 | 17 | 17
A070 | External plaster all elevations | 16 | A062 | 2026-02-02 | 2026-02-18 | FS | 1 | Plaster | 1 | 4 | 15.8 | TE≈15.8 → 16 d | 4 | 4 | 16 | 16
A071 | Flooring (common areas all floors) | 14 | A068,A069 | 2026-03-26 | 2026-04-09 | FS,FS | 3,3 | Tiling | 1 | 4 | 13.2 | TE≈13.2 → 14 d (areas from plans) | 3 | 4 | 14 | 14
A072 | Toilet waterproofing (all floors) | 4 | A069 | 2026-03-26 | 2026-03-30 | FS | 3 | Waterproofing | 1 | 3 | 2.8 | TE≈2.8 → 4 d incl. cure margin | 4 | 3 | 4 | 4
A073 | Toilet floor screed and tiling (all floors) | 2 | A072,A071 | 2026-04-09 | 2026-04-11 | FS,FS | 2,0 | Tiling | 1 | 3 | 0.9 | TE≈0.9 → 2 d | 3 | 3 | 2 | 2
A074 | Toilet wall dado tiling (all floors) | 4 | A073 | 2026-04-10 | 2026-04-14 | SS | 1 | Tiling | 1 | 3 | 3.1 | TE≈3.1 → 4 d | 3 | 3 | 4 | 4
A075 | Toilet sanitary fixtures & CP fittings (all floors) | 4 | A073,A074 | 2026-04-15 | 2026-04-19 | FS,FS | 1,1 | Plumbing/CP | 1 | 3 | 3.3 | TE≈3.3 → 4 d | 3 | 3 | 4 | 4
A076 | Door/window shutters and glazing (all floors) | 8 | A068,A069 | 2026-03-25 | 2026-04-02 | FS,FS | 2,2 | Joinery/Glazing | 1 | 4 | 8 | TE=8 d | 4 | 4 | 8 | 8
A077 | Internal painting (all floors) | 12 | A071,A075,A076 | 2026-04-21 | 2026-05-03 | FS,FS,FS | 3,2,2 | Painting | 1 | 4 | 7.1 | TE≈7.1 → duration extended to 12 d for drying/sequence & painting phases | 4 | 4 | 12 | 12
A078 | External works: ramp 1:5, approach, drainage tie-ins | 6 | A070,A058 | 2026-02-20 | 2026-02-26 | FS,FF | 2,0 | External Works | 1 | 6 | 4.2 | TE=50/12≈4.17 → 6 d (site logistics buffer applied) | 6 | 6 | 6 | 6
A079 | Final cleaning and snag rectification | 4 | A077,A078 | 2026-05-04 | 2026-05-08 | FS,FS | 1,0 | Cleaning | 1 | 6 | 3 | TE=12/4=3 → 4 d incl. snagging float | 6 | 6 | 4 | 4
A080 | Substantial completion and demobilization | 3 | A079 | 2026-05-08 | 2026-05-11 | FS | 0 | Completion/Demob | 1 | 4 | — | Admin / close-out phase, fixed 3 d | 4 | 4 | 3 | 3
Formulas:
EF = Table4[[#This Row],[ES]] + Table4[[#This Row],[Duration (days)]]

## Sheet3
Q | A written summary of how the house project is scheduled or planned.
Answer | The house is scheduled as a PDM network on a day time scale and 6‑day workweek, with deterministic durations computed by TE=q/(p×n) using take‑off quantities and labour output constants from IS 15883‑2 and IS 7272‑1.
Sequencing progresses substructure → three RC frame cycles per floor (columns → beams → slabs → stairs) → roof/mumty → masonry → frames/services → plaster/toilets → flooring/joinery/painting → external works → handover, aligned to the uploaded architectural/structural drawings.
Logic uses FS/SS links with realistic lags for access and curing (e.g., 1–2 days between pours and next shuttering, 7 days before roof waterproofing) so durations remain productivity‑based and the critical path is auditable.
Resource levelling limits concurrent demand to one formwork, one rebar, and one concreting gang, staggers trades with resource ties, and opens a second front only where workface allows safe parallelism.
Progress is controlled on a weekly cycle with a Friday site cut‑off, Monday schedule refresh, and a rolling two‑week look‑ahead, with any logic changes documented in the basis‑of‑schedule.
The schedule sheet auto‑calculates ES/EF while auxiliary columns (Duration_before_level, Crew_n, Crew_size_people) preserve traceability from workbook quantities to staffing assumptions and final levelled dates.

## Sheet4
Q | List out what are the limitations of the schedule template that you have developed for this assignment.
Answer | Quantities combine workbook take‑offs and drawing-based inferences, so any design change or re‑measurement will alter TE=q/(p×n) durations and may shift the critical path
Productivities are converted from IS 7272‑1 labour output constants and rounded to small‑project gangs, so real site outputs and crew mixes can deviate and require recalibration.
Resource leveling works by staggering activities and linking resources so that only one crew is assigned at a time (Crew_n = 1). This means the schedule assumes there’s only a single work front available. While this avoids overloading resources, it can also leave some capacity unused—unless we specifically allow multiple work fronts to run in parallel.
Fixed lags are used to represent curing times, access delays, or weather buffers, but they don’t automatically adjust for changing conditions or different trade calendars. The schedule template relies on a single 6-day calendar at the day level, and it doesn’t account for shifts or overtime work.
Some items are still outside the current scope—for example, certain procurement and approval steps, permanent utility connections, and specialized MEP works. If these are later brought into scope, additional activities and dependencies will need to be added to the schedule.

## Sheet5
Group Members
1 | Deepak Chaurasia | 220330
2 | Rahul | 220855
3 | Shreyansh | 221031