## Baseline_Schedule
Act ID | Activity Name | Duration (days) | Predecessor | Planned Start | Planned Finish | Daily Start of an activity and how much its completed at the end of that day(On Each day basis) | Actual Finish(On site reality) Can be filled manually after the 100% complete of an activity | % Complete(Each day updation) | Remaining Duration(Counted wrt total %complete of an activity from each day) | Revised Finish | Status
A | Mobilization | 3 |  | 2025-11-10 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 100 | 0 | 2025-11-13 | Completed
B | Site survey & setting out | 2 | A | 2025-11-14 | 2025-11-16 | 2025-11-16 |  | 90 | 1 | 2025-11-17 | On Schedule
C | Excavation | 7 | B | 2025-11-17 | 2025-11-24 | 2025-11-20 |  | 10 | 7 | 2025-11-27 | On Schedule
D | PCC & Subbase | 3 | C | 2025-11-25 | 2025-11-28 | 2025-11-26 |  | 25 | 3 | 2025-11-29 | On Schedule
E | Footing formwork & rebar | 5 | D | 2025-11-29 | 2025-12-04 | 2025-11-30 |  | 20 | 4 | 2025-12-04 | On Schedule
F | Footing concreting | 2 | E | 2025-12-05 | 2025-12-07 | 2025-12-06 |  | 50 | 1 | 2025-12-07 | On Schedule
G | Footing curing & backfill | 7 | F | 2025-12-08 | 2025-12-15 | 2025-12-10 |  | 24 | 6 | 2025-12-16 | On Schedule
H | Columns GF – formwork & rebar | 6 | G | 2025-12-16 | 2025-12-22 | 2025-12-18 |  | 34 | 4 | 2025-12-22 | On Schedule
I | GF slab formwork & reinforcement | 8 | H | 2025-12-23 | 2025-12-31 | 2025-12-25 |  | 30 | 6 | 2025-12-31 | On Schedule
J | GF slab concreting | 2 | I | 2026-01-01 | 2026-01-03 | 2026-01-01 |  | 10 | 2 | 2026-01-03 | On Schedule
K | GF slab curing & masonry start | 10 | J | 2026-01-04 | 2026-01-14 | 2026-01-08 |  | 25 | 8 | 2026-01-16 | On Schedule
L | GF masonry & finishes | 15 | K | 2026-01-15 | 2026-01-30 | 2026-01-22 |  | 65 | 6 | 2026-01-28 | On Schedule
[5 empty] | Column | Formula | Description
[5 empty] | Planned Start | =IF(Dx="",DATE(2025,11,10),VLOOKUP(Dx,$A$2:$L$13,6,FALSE)+1) | If no predecessor → project start; else start after predecessor’s finish
[5 empty] | Planned Finish | =Ex+Cx | Duration added to start
[5 empty] | Remaining Duration | =IF(Ix="",Cx,IF(Ix=100,0,CEILING(Cx*(1-Ix/100)))) | Auto updates with % complete
[5 empty] | Revised Finish | =IF(Gx<>"",Gx+Jx,Fx) | If started, shifts finish date based on remaining duration
[5 empty] | Status | =IF(Ix=100,"Completed",IF(AND(Gx="",TODAY()>Ex),"Not Started (Delay)",IF(AND(Gx<>"",TODAY()>Fx),"In Progress (Slower)",IF(AND(Gx="",TODAY()<Ex),"Not Planned Yet","On Schedule")))) | Auto-evaluates live site condition
| Considered a simple CPM network just for explanation. Can extrapolate this to a PDM as well. |  |  |  |  | Some Succeding Activities can start even after only some % of previous activity has finished.

## Delay_Impact_Summary
Act ID | Activity Name | Planned Finish | Revised Finish | Delay (days) | Successor(s) | Successor Planned Start | New Start (after update)
A | Mobilization | 2025-11-13 | 2025-11-13 | 0 | B | 2025-11-14 | 2025-11-14
B | Site survey & setting out | 2025-11-16 | 2025-11-17 | 1 | C | 2025-11-17 | 2025-11-18
C | Excavation | 2025-11-24 | 2025-11-27 | 3 | D | 2025-11-25 | 2025-11-28
D | PCC & Subbase | 2025-11-28 | 2025-11-29 | 1 | E | 2025-11-29 | 2025-11-30
E | Footing formwork & rebar | 2025-12-04 | 2025-12-04 | 0 | F | 2025-12-05 | 2025-12-05
F | Footing concreting | 2025-12-07 | 2025-12-07 | 0 | G | 2025-12-08 | 2025-12-08
G | Footing curing & backfill | 2025-12-15 | 2025-12-16 | 1 | H | 2025-12-16 | 2025-12-17
H | Columns GF – formwork & rebar | 2025-12-22 | 2025-12-22 | 0 | I | 2025-12-23 | 2025-12-23
I | GF slab formwork & reinforcement | 2025-12-31 | 2025-12-31 | 0 | J | 2026-01-01 | 2026-01-01
J | GF slab concreting | 2026-01-03 | 2026-01-03 | 0 | K | 2026-01-04 | 2026-01-04
K | GF slab curing & masonry start | 2026-01-14 | 2026-01-16 | 2 | L | 2026-01-15 | 2026-01-17
L | GF masonry & finishes | 2026-01-30 | 2026-01-28 | -2 |  |  | 2026-01-29
Considered a simple CPM network just for explanation. Can extrapolate this to a PDM as well.

## Daily_Progress_Report
Date | Act ID | Activity Name | Planned % (Cumulative) | Actual % (Cumulative) | Daily Progress (%) | Variance (%)
2025-11-10 | A | Mobilization | 33 | 30 | 30 | -3
2025-11-11 | A | Mobilization | 67 | 70 | 40 | 3
2025-11-12 | A | Mobilization | 100 | 100 | 30 | 0
2025-11-14 | B | Site survey & setting out | 50 | 50 | 50 | 0
2025-11-15 | B | Site survey & setting out | 100 | 100 | 50 | 0
2025-11-16 | C | Excavation | 0 | 0 | 0 | 0
2025-11-17 | C | Excavation | 14 | 10 | 10 | -4
2025-11-18 | C | Excavation | 29 | 30 | 20 | 1
2025-11-19 | C | Excavation | 43 | 40 | 10 | -3
2025-11-20 | C | Excavation | 57 | 50 | 10 | -7
2025-11-21 | C | Excavation | 71 | 75 | 25 | 4
2025-11-22 | C | Excavation | 86 | 80 | 5 | -6
2025-11-23 | C | Excavation | 100 | 100 | 20 | 0
Similarly, progress of all the activities can be shown like this.

## Steps
Step 1 – Set up your Excel workbook
Create three sheets:
Baseline Schedule – planned start, finish, duration, predecessors, and resources.
Daily Progress Report (DPR) – actual daily site updates.
Delay/Impact Summary – automatic calculation of delays and effects on successors.
Step 2 – List activities(Randomly taken for ex)
Mobilization
Site survey & setting out
Excavation
PCC & Subbase
Footing formwork & rebar
Footing concreting
Footing curing & backfill
Columns GF – formwork & rebar
GF slab formwork & reinforcement
GF slab concreting
GF slab curing & masonry start
GF masonry & finishes
Step 3 – Add planned schedule data
Formulas:
Planned Finish = Planned Start + Duration
Step 4 – Create DPR sheet for daily entry
Formulas:
Planned % = (Days elapsed ÷ Total Duration) × 100
Remaining Duration = =IF(I2="",C2,IF(I2=100,0,CEILING(C2*(1-I2/100),1)))
Revised Finish =(=IF(G2<>"",G2+J2,F2))
%Complete= On site how much work is completed.
Delay (days) = =Revised Finish - Planned Finish
Step 5 – Daily update process
Each day on site:
Record which activities were worked on.
Enter Actual % Complete, Quantity Done, and Remarks.
Excel updates Remaining Duration, Revised Finish, and Delay automatically.
Step 6 – Update schedule dynamically
If % Complete < Planned %, activity is delayed → successor’s start shifts forward.
If % Complete > Planned %, activity is ahead → float increases.
Delay Impact Sheet summarizes total project delay = max(Revised Finish – Planned Finish).
Step 7 – Generate DPR summary output
Formula for Overall Progress %:
Progress=(=AVERAGEIFS(%Complete, Activity, "<>"))
Step 8 – Use for decision making
Identify critical path and delayed activities.
Reschedule labour/material supply.
Communicate daily to project manager and client.
Step 9 – IS Codes Referenced
For schedule and manpower estimation:
IS 7272 (Part 1 & 2): 1974 – Recommendations for labour output in building work.
IS 15883 (Part 1 to 5) – Planning and scheduling in construction.
IS 1200 series – Methods of measurement for construction quantities.
IS 14580:1998 – Guidelines for preparation of bar charts and network diagrams (PERT/CPM).

## Grp Members
Shreyansh | 221031
Deepak Chaurasia
Rahul Singh